## Overview
Accelerate AI Growth and Adoption - Methods and Comments
Report Summary
Base | CX FY26 V2MOM - NEW
H2 Value | Accelerate AI Growth and Adoption
Top-Level Methods | 4
Sub-Methods | 22
Dated Top-Level Update Rows | 15
Dated Sub-Method Update Rows | 43
Airtable Record Comments | 0
Extraction Note | Dated comments come from TL/SM update table commentary fields; Airtable record comments are listed separately when present.

## Top-Level Methods
Top-Level Method | Method Owner Name | Status Owner | Team | Measure Description | FY26 Measure | Current Status | Current Actual | Current Commentary | Previous Status | Previous Actual | Previous Commentary | Status Update Date | Reporting Period | Sub-Method Count | Dated Update Count
Enable the field and partners to confidently sell AI | Abhiram Kramadhati |  | AI Solution Consulting Group | Published customer references or completed events for CX AI products | 20 references/events | On Track | 78 usecases published to the usecase library. | 78 usecases published to the usecase library. Many of these are in the pipeline to become externally referencable. | Off Track/Delayed | 2 | While our overall pace of new case study publication is currently tracking behind our initial target, we have strategically pivoted our approach to prioritize depth and long-term value. We are currently averaging two new CX-focused case studies per month; however, we have redirected resources to retroactively update our existing library with new AI-driven outcomes as our customers evolve. By enhancing these proven success stories with AI-specific metrics rather than solely focusing on new volume, we are creating a more compelling and 'sticky' narrative for our enterprise prospects, which better supports our long-term AI adoption goals. | 2026-06-11 11:13 | Jun 4 (June MBR) | 8 | 4
Make AI easy to start and hard to abandon | Abhiram Kramadhati | Maurice Lopes | Sales-COE | % attach rate for AI Agent & Assistant (against total billed WxCC customers) | - AI Agent - 20% attach - AI Assistant - 10% attach | At Risk | - WxCC Installed base: - \- AI Agent: 10% - \- AI Assistant: 10% - \- Overall Attach: 13% - New orders: - \- AI Agent: 20% - \- AI Assistant: 13% - \- Overall Attach: 24% | For Q4, we are manually reaching out to the RMs to drive attach - atleast uncommitted so that the activation is done. By end of Q4, we will report on uncommitted attach as well because that is an important metric - they are not being reflected today. | Off Track/Delayed | - **WxCC Installed base:** - \- AI Agent: 10% - \- AI Assistant: 10% - \- Overall Attach: 13% - **New orders:** - \- AI Agent: 20% - \- AI Assistant: 13% - \- Overall Attach: 24% | Cisco attach and adoption challenges are primarily due to Offer Setup, Positioning and Coverage challenges. Next steps: GTM plan for better AI positioning and coverage. Product plan to support with pre-built use cases and vertical focus. | 2026-06-11 11:15 | Jun 4 (June MBR) | 7 | 6
Scale AI across platform and ecosystem | Abhiram Kramadhati |  | AI Solution Consulting Group | Scale AI ecosystem impact through continuous customer-led use case validation and integrated cross-Cisco GTM motions. | [9 empty] | 3 | 0
Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | Chang Chang | Manali Dongre | Cloud Product Management | Number of capabilities enabled | **8 capabilities (rollup of sub measures)** | Off Track/Delayed | 1.5 | - Reporting for AI QM - Human Agent reports in Analyzer will be in June. For AI Agents planned for July beta. - Reporting for AI Assistant - Delayed to Q1/Q2FY27 due to prioritizing AI Assistant Get Well Plan. - Reporting for AI WFM - In Planning. Planned for Q1FY27 - Analyzer feature - Comprehensive Home page on track for July GA. - Analyzer feature - Streamlined create visualization - August/Sept beta. GA will be delayed to Q1FY27. - AI Assistant delivered in PowerBI | At Risk | 2 features committed in Q3 FY26. May get delayed to Q4 FY26 (AI Assistant Usage Dashboard under development; Analyzer Reports for Quality Management in Discovery) | - 5 features scheduled GA in Q4 FY26. - 1 feature delayed from Q4 FY26 to Q1 FY27 (AI WFM Reports). | 2026-06-11 16:16 | Jun 4 (June MBR) | 4 | 5

## Sub-Methods
Top-Level Method | Sub-Method | Owner - Supporting Method | Status Owner | Team | Measure Description | FY26 Measure | Current Status | Current Actual | Current Commentary | Previous Status | Previous Actual | Previous Commentary | Status Update Date | Reporting Period | Dated Update Count | FIRA Count | FIRAs | FIRA Feature Names | FIRA Latest Release Quarter Status | FIRA JIRA Status | FIRA JIRA Feature State | FIRA Latest Update Quarter | FIRA Market Access | FIRA CLUS Payload Items | FIRA CLUS Payload Items NEW
Enable the field and partners to confidently sell AI | Public AI customer endorsemenets | Ramy Riad | Maurice Lopes | AI Solution Consulting Group | Ensure publicly published reference stories for AI use cases across the different AI products | At least 20 reference customers including 5 on-prem and 2 for each of the new products under product incubation | On Track | Published 11 public AI customer references in Q3 | Published 11 public AI customer references in Q3, now fully available to support internal field teams and accelerate AI adoption. | On Track |  | Multiple customers went live: Seminole Hardrock, Missippi Gulf Coast. Marketing team is also working on case studies, we had the Uniting webinar publicly published in Feb. | 2026-05-08 03:34 | May 19 (Q3 QBR) | 2 | 0
Enable the field and partners to confidently sell AI | Establish AI demo enablement and availability | Abhiram Kramadhati | Maurice Lopes | AI Solution Consulting Group | Ensure every released Cisco AI capability is demonstrable through standard Cisco demo mechanisms, supported by a reusable demo library | - 100% of released Cisco AI features demonstrable within 7 days of GA - All priority verticals have one end-to-end AI demo available - Add 5 new or updated AI demos/qtr to demo library | On Track | Demo Library is active, but need to discuss with Jitesh on when to transition this over to his team. | Demo Library is active, but need to discuss with Jitesh on when to transition this over to his team. | On Track |  | Demo Library is active, but need to discuss with Jitesh on when to transition this over to his team. | 2026-05-13 01:58 | May 19 (Q3 QBR) | 2 | 0
Enable the field and partners to confidently sell AI | Verticalised approach and focus for AI | Holger Esser |  | AI Solution Consulting Group | Establish a verticalized AI approach that enables Cisco to show up with clear, focused relevance in priority markets. | Established plan and execution for 3 verticals | On Track | To accelerate our verticalized strategy, we have selected InterSystems as our strategic partner to provide the HL7 gateway, a critical foundation for unlocking our AI-driven healthcare use cases. | By securing full alignment with the Product Management team, we have validated our technical roadmap and confirmed our path forward. We are now finalizing the Statement of Work, setting the stage to transition this initiative into active execution. | On Track | - Healthcare: Team delivered 4 use cases, including customer documentation and partner documentation. This includes Epic and Athena (2nd in market share). Marketing slides were delivered. - Working on getting into the Athena marketspace. |  | 2026-05-06 22:01 | May 19 (Q3 QBR) | 3 | 0
Enable the field and partners to confidently sell AI | Expand the AI use-case library by vertical and whitespace | David Veevers | Maurice Lopes | AI Solution Consulting Group | Maintain a continuously published, always-referenceable AI use-case library that showcases real, data-backed customer outcomes across use cases and verticals. | Externally published usecase library across verticals | On Track | 100% of live use cases are now documented and accessible to internal resources. | - Scaled to 71 published use cases FTD (+11 this period). - Healthcare expansion will utilize our existing, validated deployment model to accelerate time-to-market. | On Track |  | Usecase Library is active and currently at 60+ usecases. | 2026-05-08 03:28 | May 19 (Q3 QBR) | 2 | 0
Enable the field and partners to confidently sell AI | New Product References | David Veevers | Maurice Lopes | AI Solution Consulting Group | Ensure reference use cases for all new AI products such as AIQM, AI routing, MCP A2A are in place | Minimum 2 reference customers per product: AIQM, AI Routing and MCP/A2A | On Track | - 3 AI QM references. - 2 A2A/MCP references. | Secured 5 new product references (3 AI QM, 2 A2A/MCP). | On Track |  | 3 customers for AI QM and 2 for AI Routing are under trial, and 1 customer underway for MCP/A2A | 2026-05-08 03:31 | May 19 (Q3 QBR) | 2 | 0
Enable the field and partners to confidently sell AI | AI Cookbooks | Chandramouli Vaithiyanathan | Maurice Lopes | AI Solution Consulting Group | Create reference and repeatable playbooks that can be used in every AI SCG deployment to show what good looks like | Published AI Agent cookbook and used in 100% of all AI Agents developed by SCG and integrations available in the MCP factory. | On Track |  | CookBook will be made public on Jun 5th | On Track | Cookbook complete, pending review before publishing it. | The AI Cookbook is finalized and currently undergoing internal review. Once approved, this resource will be published externally to provide partners with actionable guidance on best practices and, accelerating AI deployment], directly supporting our cloud adoption goals. | 2026-06-02 20:33 | Jun 4 (June MBR) | 3 | 0
Enable the field and partners to confidently sell AI | Internal AI Evangelization | Chandramouli Vaithiyanathan | Maurice Lopes | AI Solution Consulting Group | Plan for sharing the right details, both technical and from a product positioning perspective, with the internal field and constantly ensure that they are updated on all things AI | Have repeatable and shareable external messaging for the sales and the partner community. This can be monthly calls recorded with guests or any other category | On Track | Established recurring 30-minute monthly AI enablement session within the WebEx Experts call. | Successfully partnered with Product Management to secure a standing monthly slot on the WebEx Experts call. This provides a dedicated, scalable channel to evangelize AI capabilities to Sales, Solutions Engineers, and cross-functional teams, ensuring consistent messaging and technical readiness across the field. | On Track |  | Chandra is working with Zack to get the Experts call to become the standing call for AI Experts, rather than the standalone call that happens today. | 2026-05-12 15:18 | May 19 (Q3 QBR) | 2 | 0
Enable the field and partners to confidently sell AI | MCP Factory | Niko Theologitis | Maurice Lopes | AI Solution Consulting Group | Provide a library of MCP servers that will allow the Cisco field to build integrations into AI agents that will showcase the best of Cisco and the best of our experience. | Have an established and published list of MCP integrations that are used by all SCG-built AI agents, along with the details of references for customer deployments. | On Track | 11 | Launched the MCP Factory within the AI Customer Hub, delivering 11 MCP servers in Q3 (exceeding the target of 5). This framework enables secure, autonomous integrations for Athena, Salesforce, and ServiceNow, streamlining field deployment of AI agents. | On Track |  |  | 2026-05-08 03:43 | May 19 (Q3 QBR) | 2 | 0
Make AI easy to start and hard to abandon | Create AI sales enablement plays | Darren Verette | Andrew Cammer | Sales-COE | [10 empty] | 0 | 0
Make AI easy to start and hard to abandon | Create AI partner enablement plays | Darren Verette | Andrew Cammer | Sales-COE | [10 empty] | 0 | 0
Make AI easy to start and hard to abandon | Execute AI seeding plans | Abhiram Kramadhati |  | Collab GTM | Seed Cisco AI adoption at scale by enabling low-friction entry offers that activate customers and partners across contact centers. | A formal AI seeding offer that can be used by Cisco Customers and Partners | [8 empty] | 0 | 0
Make AI easy to start and hard to abandon | Create a unified AI trial experience | Tom Clifford |  | Collab GTM | [10 empty] | 0 | 0
Make AI easy to start and hard to abandon | Define and operationalize in-life AI adoption motions | Marcus Quinn |  | Customer Success | - Create an AI white space grid - Deliver ROI data for each AI implementation | - Create an AI white space grid - Publish ROI data for >75% of new AI deployments | On Track | ROI being collected where available - need to find a way with Dave Veevers on aggregating and making it reportable | - Use case library: <https://airtable.com/appUJj24OxwiVXkGr/pag6EmPvdibW1rELf> (16 use cases) - Customer/sector use cases: https://airtable.com/appUJj24OxwiVXkGr/pagZ6G30hwZKJ4TaI?aojWI=allRecords | On Track |  | Continuing work with DV's Customer Hub Airtable to turn into whitespace/use case library. | 2026-04-20 12:52 | May 19 (Q3 QBR) | 4 | 0
Make AI easy to start and hard to abandon | Publish Re-usable AI Agents | Chandramouli Vaithiyanathan | Maurice Lopes | AI Solution Consulting Group | As the use case library is built out, create a publishable version of use cases and publish them into the product | Published at least 15 pre-built agents as templates in the product. Also have a technical blog published for each of these use case categories. | Off Track/Delayed | Two re-usable AI Agent templates published. | While we successfully deployed two templates this quarter, progress was paced by a dependency on the AI Cookbook. With the Cookbook now finalized, we have cleared the primary blocker and are positioned to accelerate the development and release of the remaining templates in the coming period. | Planning |  |  | 2026-05-12 15:19 | May 19 (Q3 QBR) | 2 | 0
Make AI easy to start and hard to abandon | Dog and Pony Show | Dan Mathews |  | AI Solution Consulting Group |  | N/A | At Risk | Met with the account teams for all target GES opportunities and segmented them based on relationship and investment. SCG and COW are engaged in the investment accounts, but executive / GTM involvement is required in the majority of GES accounts to rebuild the relationship and capture mindshare. |  | Planning | N/A | We are actively collaborating with the Collaboration GTM leadership to transition this framework into their portfolio, ensuring long-term scalability and seamless integration into our broader go-to-market strategy. | 2026-05-31 18:44 | Jun 4 (June MBR) | 3 | 0
Scale AI across platform and ecosystem | Execute third-party AI POCs where strategically required | Holger Esser |  | AI Solution Consulting Group | Continuously experiment with AI alongside customers to identify and validate new use cases that inform product strategy | An established innovation council with a refernce library of customer stories who are co-innovating with Cisco | On Track | Successfully conducted the US Innovation Council meeting, maintaining an average attendance of 25–30 participants from a core group of 55 customer members. | The Innovation Council continues to serve as a high-value feedback loop, enabling our Product Management teams to rigorously vet product viability and roadmap alignment. Participants have expressed strong appreciation for the opportunity to directly influence our product backlog and feature prioritization. Given this positive engagement, we are currently planning to scale this model into additional geographies by the end of the fiscal year to broaden our global customer perspective. | On Track |  | We had meetings for Neural Fabric with NYU Langone and for Ez Dubz with about 5 customers, on track and progressing. | 2026-05-07 16:14 | May 19 (Q3 QBR) | 2 | 0
Scale AI across platform and ecosystem | Launch AI-specific One Cisco GTM initiatives | Abhiram Kramadhati | Maurice Lopes | AI Solution Consulting Group | Explore cross-Cisco AI GTM initiatives to create differentiated, sticky enterprise outcomes by leveraging Cisco’s full AI portfolio | Customer validated usecases for wider AI portfolio of Cisco | On Track | 5 active POCs with EzDubs. | We have successfully scaled our engagement with EzDubs, currently managing five active POCs that are demonstrating strong potential for enterprise outcomes. Regarding the Neuralfabric target, we conducted a strategic assessment and determined that this integration does not align with our current FY26 deliverables; consequently, we have deprioritized this effort to focus resources on higher-impact opportunities. | Planning |  |  | 2026-05-13 02:03 | May 19 (Q3 QBR) | 2 | 0
Scale AI across platform and ecosystem | AI deployment/activation plan (FDE Model) | Prakash Kini | Maurice Lopes | Technical Solutioning | AI Activations | 100% of activated customers with AI orders already live on WxCC: | Planning | N/A | Operationalized the FDE model in BETA phase as of Q3, establishing a strategic framework to accelerate AI adoption and usage revenue. | Planning | TBD | This method needs to be discussed with Vinod and perhaps re-purpose it given the new direction of creating a FDE team (Foward deployed Engineer) for help accelerate AI use cases, value realization and implementation. | 2026-05-13 17:05 | May 19 (Q3 QBR) | 4 | 0
Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | Deliver in-life management telemetry for AI | Manali Dongre | Manali Dongre | Cloud Product Management | Number of features delivered | 3 features/capabilities | At Risk | 1.5 features done | - AI Assistant in PowerBI - Done - Feature usage metrics - 90% of usage metrics needed by In-Life and Customer Success teams were available in Amplitude and PowerBI. There is a retention issue that is being worked on with WAP teams. - Operational metrics - 30% available in Amplitude and are made available. For remaining, approach being explored with the Data team to get the data into Splunk (since Platform team has moved Grafana metrics to Splunk and moving to Splunk is needed for TAC). Solution being explored to see whether reports need to be built in Splunk or PowerBI. Targeted for something in Q4 else will slip to Q1. However, PM driving this area was impacted and so looking to transition this to another PM | At Risk | 1.5 feature | - AI Assistant in PowerBI - Done - Feature usage metrics - 90% of usage metrics needed by In-Life and Customer Success teams were available in Amplitude and so have shared them with the team for review. Working with PowerBI team to build dashboards for the same. - Operational metrics - 30% available in Amplitude and are made available. For remaining, approach being explored with the Data team to get the data into Splunk (since Platform team has moved Grafana metrics to Splunk and moving to Splunk is needed for TAC). Solution being explored to see whether reports need to be built in Splunk or PowerBI. Targeted for something in Q4 else will slip to Q1 | 2026-05-27 12:18 | Jun 4 (June MBR) | 4 | 3 | - WXCC-11259 - WXCC-14031 - WXCC-14035 | - AI Assistant- Feature usage metrics dashboard (PowerBI) - Telemetry dashboard- Operational Metrics/ KPIs - Telemetry dashboard- Feature usage metrics | - WXCC-11259: On Track - WXCC-14031: Slipped - WXCC-14035: On Track | - WXCC-11259: Development - WXCC-14031: DISCOVERY - WXCC-14035: Development | - WXCC-11259: Green - WXCC-14031: Green - WXCC-14035: Green | - WXCC-11259: FY26-Q4 - WXCC-14031: FY27-Q1 - WXCC-14035: FY26-Q4
Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | Enhance reporting & analytics for AI products including ROI | Manali Dongre | Manali Dongre | Cloud Product Management | Number of features delivered | 5 features/capabilities. Excluding observability. | Off Track/Delayed | 0 features | - Reporting for AI QM - Human Agent reports in Analyzer will be in June. For AI Agents planned for July beta. - Reporting for AI Assistant - Delayed to Q1/Q2FY27 due to prioritizing AI Assistant Get Well Plan. - Reporting for AI WFM - In Planning. Planned for Q1FY27 - Analyzer feature - Comprehensive Home page on track for July GA. - Analyzer feature - Streamlined create visualization - August/Sept beta. GA will be delayed to Q1FY27. | Off Track/Delayed | 2 feature | - Reporting for AI QM - Human Agent reports in Analyzer next month. For AI Agents planned for July. - Reporting for AI Assistant - Delayed to Q1/Q2FY27 due to prioritizing AI Assistant Get Well Plan. - Reporting for AI WFM - In Planning. Planned for Q1FY27 - Analyzer feature - Comprehensive Home page on track for July GA. - Analyzer feature - Streamlined create visualization - July end Beta. GA will be delayed to Q1FY27. | 2026-05-27 12:16 | Jun 4 (June MBR) | 4 | 5 | - WXCC-10116 - WXCC-14282 - WXCC-1517 - WXCC-4266 - WXCC-9833 | - Analyzer Reports for QM - WFM Reports - Analyzer - Reimagine the create flow for visualizations using a wizard like approach - AI Assistant Analyzer Dashboard holistic enhancements - Analyzer - Reimagine the homepage with comprehensive reports and dashboards management | - WXCC-10116: On Track - WXCC-14282: On Track - WXCC-1517: On Track - WXCC-4266: On Track - WXCC-9833: On Track | - WXCC-10116: DISCOVERY - WXCC-14282: Capture - WXCC-1517: DISCOVERY - WXCC-4266: Backlog - WXCC-9833: Development | - WXCC-10116: Green - WXCC-14282: Green - WXCC-4266: Blue - WXCC-9833: Green | - WXCC-10116: FY26-Q3 - WXCC-14282: FY27-Q1 - WXCC-1517: FY26-Q4 - WXCC-4266: FY26-Q4 - WXCC-9833: FY27-Q1 |  | WXCC-10116: true | - WXCC-10116: WEM - WXCC-14282: WEM
Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | Upsell AI capabilities at on-prem renewal | Darren Verette | Andrew Cammer | Sales-COE |  | Attach AI to >20% of On Prem Renewals | [6 empty] | 2026-02-02 20:40 |  | 0 | 0
Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | Deliver AI innovation for CCE on-prem and hybrid deployments | Girish Variyath | Girish Variyath | On Prem Product Management | Release AI Agent & Assistant features to CCE customers and have live customers. | - GA of Features (Voice Scripted AI Agent - H1; Digital & Scripted/Autonomous AI Agent - H2; Two AI Assistant features - H1; 5 Beta AI Assistant features - H1 - 10 customers with AI trials | [6 empty] | 2026-02-02 20:40 |  | 0 | 1 | CB-1355 | AI Agent Summary (Voice) | CB-1355: On Track | CB-1355: Early Access | CB-1355: Green | CB-1355: FY27-Q1 |  | CB-1355: true | CB-1355: On-Prem Hero Items

## TL Dated Updates
Top-Level Method | Update Date | Reporting Month | Reporting Period | Status | Actual | Commentary | Obstacles
Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | 2026-03-10 04:00 |  | Mar 19 (March MBR) | On Track | 0 feature | 4 features are in capture, 1 in Soft Commit, 1 in Backlog and 2 discovery
Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | 2026-04-01 11:11 |  | Apr 7 (April MBR) | On Track | 2 features on track | 1 feature in discovery and 1 capture stage | "Clarity on requirements from field (SCG, COE, in-life teams)"
Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | 2026-04-23 01:09 | Month 1 | May 19 (Q3 QBR) | Off Track/Delayed | 2 features committed in Q3 FY26 delayed to Q4 FY26 | - 7 features now scheduled GA in Q4 FY26 - 1 feature delayed to Q1 FY27 (AI WFM Reports) | "Clarity on requirements from field (SCG, COE, in-life teams)"
Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | 2026-04-23 08:29 | Month 1 | May 19 (Q3 QBR) | At Risk | 2 features committed in Q3 FY26. May get delayed to Q4 FY26 (AI Assistant Usage Dashboard under development; Analyzer Reports for Quality Management in Discovery) | - 5 features scheduled GA in Q4 FY26. - 1 feature delayed from Q4 FY26 to Q1 FY27 (AI WFM Reports). | "Clarity on requirements from field (SCG, COE, in-life teams)"
Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | 2026-06-11 16:16 | Month 2 | Jun 4 (June MBR) | Off Track/Delayed | 1.5 | - Reporting for AI QM - Human Agent reports in Analyzer will be in June. For AI Agents planned for July beta. - Reporting for AI Assistant - Delayed to Q1/Q2FY27 due to prioritizing AI Assistant Get Well Plan. - Reporting for AI WFM - In Planning. Planned for Q1FY27 - Analyzer feature - Comprehensive Home page on track for July GA. - Analyzer feature - Streamlined create visualization - August/Sept beta. GA will be delayed to Q1FY27. - AI Assistant delivered in PowerBI | "Clarity on requirements from field (SCG, COE, in-life teams)"
Enable the field and partners to confidently sell AI | 2026-01-05 05:00 |  | Jan 8 (January MBR) | On Track | 9 references published | More usecases have gone live in Q2 including POCs of larger deals like CHN that are not included here. Other significant ones include RoomsToGo and FHB. We should see more AI Assistant customers go live in Q3 as features are becoming GA.
Enable the field and partners to confidently sell AI | 2026-03-05 05:00 |  | Feb 6 (February MBR) | On Track | - Following case studies underway: - 1\. Uniting - 2\. Cisco IT - 3\. Al Moosa Hospital - 4\. GetixHealth - 5\. Rotech Healthcare - 6\. Deutsche Telekom - 7\. Yum! Brands
Enable the field and partners to confidently sell AI | 2026-05-13 04:31 | Month 1 | May 19 (Q3 QBR) | Off Track/Delayed | 2 | While our overall pace of new case study publication is currently tracking behind our initial target, we have strategically pivoted our approach to prioritize depth and long-term value. We are currently averaging two new CX-focused case studies per month; however, we have redirected resources to retroactively update our existing library with new AI-driven outcomes as our customers evolve. By enhancing these proven success stories with AI-specific metrics rather than solely focusing on new volume, we are creating a more compelling and 'sticky' narrative for our enterprise prospects, which better supports our long-term AI adoption goals.
Enable the field and partners to confidently sell AI | 2026-06-11 11:13 | Month 2 | Jun 4 (June MBR) | On Track | 78 usecases published to the usecase library. | 78 usecases published to the usecase library. Many of these are in the pipeline to become externally referencable.
Make AI easy to start and hard to abandon | 2026-01-09 05:00 |  | Jan 8 (January MBR) | On Track | - \- AI Agent - 8% attach - \- AI Assistant - 7% attach | AI Attach rates continue to increase, and while the overall attach across the base is low but the attach with new deals is very healthy at 26%.
Make AI easy to start and hard to abandon | 2026-03-20 04:00 |  | Feb 6 (February MBR) | On Track | - AI Agent: 8% - AI Assistant: 8% - Overall Attach: 11% - New orders: 34% | - AI Attach rates continue to increase, with the overall attach rate at 11% having increased from 9% in Q2 - •New deals have significantly higher traction, with 32% of new deals having AI attached, which was 27% in Q2 - •New deals are seeing AI consistently as evident in early Q3 deals as well.
Make AI easy to start and hard to abandon | 2026-04-02 03:42 |  | Apr 7 (April MBR) | On Track | - AI Agent: 9% - AI Assistant: 8% - Overall Attach: 11% - New orders: 30% | - AI Attach rates continue to increase, with the overall attach rate at 11% having increased from 9% in Q2 - New deals have significantly higher traction, with 30% of new deals having AI attached, which was 27% in Q2.
Make AI easy to start and hard to abandon | 2026-04-23 03:08 | Month 1 | May 19 (Q3 QBR) | Off Track/Delayed | - **WxCC Installed base:** - \- AI Agent: 9% - \- AI Assistant: 9% - \- Overall Attach: 12% - **New orders:** - \- AI Agent: 20% - \- AI Assistant: 25% - \- Overall Attach: 31% | Cisco attach and adoption challenges are primarily due to Offer Setup, Positioning and Coverage challenges. Next steps: GTM plan for better AI positioning and coverage. Product plan to support with pre-build usecases and vertical focus starting with healthcare.
Make AI easy to start and hard to abandon | 2026-06-03 12:14 | Month 2 | Jun 4 (June MBR) | Off Track/Delayed | - **WxCC Installed base:** - \- AI Agent: 10% - \- AI Assistant: 10% - \- Overall Attach: 13% - **New orders:** - \- AI Agent: 20% - \- AI Assistant: 13% - \- Overall Attach: 24% | Cisco attach and adoption challenges are primarily due to Offer Setup, Positioning and Coverage challenges. Next steps: GTM plan for better AI positioning and coverage. Product plan to support with pre-built use cases and vertical focus.
Make AI easy to start and hard to abandon | 2026-06-11 11:15 | Month 2 | Jun 4 (June MBR) | At Risk | - WxCC Installed base: - \- AI Agent: 10% - \- AI Assistant: 10% - \- Overall Attach: 13% - New orders: - \- AI Agent: 20% - \- AI Assistant: 13% - \- Overall Attach: 24% | For Q4, we are manually reaching out to the RMs to drive attach - atleast uncommitted so that the activation is done. By end of Q4, we will report on uncommitted attach as well because that is an important metric - they are not being reflected today.

## SM Dated Updates
Top-Level Method | Sub-Method | Update Date | Reporting Month | Reporting Period | Status | Actual | Commentary | Obstacles
Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | Deliver in-life management telemetry for AI | 2026-03-19 04:00 |  | Mar 19 (March MBR) | On Track | 0 features | All 3 features are in capture stage
Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | Deliver in-life management telemetry for AI | 2026-04-01 06:47 |  | Apr 7 (April MBR) | On Track | 1 feature | WXCC-14031 - will build this as a bot to get started. | "Clarity on the data requirements (e.g., What data, normalization, etc.)"
Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | Deliver in-life management telemetry for AI | 2026-05-12 06:45 | Month 1 | May 19 (Q3 QBR) | At Risk | 1.5 feature | - AI Assistant in PowerBI - Done - Feature usage metrics - 90% of usage metrics needed by In-Life and Customer Success teams were available in Amplitude and so have shared them with the team for review. Working with PowerBI team to build dashboards for the same. - Operational metrics - 30% available in Amplitude and are made available. For remaining, approach being explored with the Data team to get the data into Splunk (since Platform team has moved Grafana metrics to Splunk and moving to Splunk is needed for TAC). Solution being explored to see whether reports need to be built in Splunk or PowerBI. Targeted for something in Q4 else will slip to Q1 | "Clarity on the data requirements (e.g., What data, normalization, etc.)"
Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | Deliver in-life management telemetry for AI | 2026-05-27 12:18 | Month 2 | Jun 4 (June MBR) | At Risk | 1.5 features done | - AI Assistant in PowerBI - Done - Feature usage metrics - 90% of usage metrics needed by In-Life and Customer Success teams were available in Amplitude and PowerBI. There is a retention issue that is being worked on with WAP teams. - Operational metrics - 30% available in Amplitude and are made available. For remaining, approach being explored with the Data team to get the data into Splunk (since Platform team has moved Grafana metrics to Splunk and moving to Splunk is needed for TAC). Solution being explored to see whether reports need to be built in Splunk or PowerBI. Targeted for something in Q4 else will slip to Q1. However, PM driving this area was impacted and so looking to transition this to another PM | "Clarity on the data requirements (e.g., What data, normalization, etc.)"
Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | Enhance reporting & analytics for AI products including ROI | 2026-03-19 04:00 |  | Mar 19 (March MBR) | On Track | 0 features | 1 feature in capture, 1 in Soft Commit, 1 in Backlog and 2 discovery
Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | Enhance reporting & analytics for AI products including ROI | 2026-04-01 08:24 |  | Apr 7 (April MBR) | On Track | Analyzer Reports for QM on track | On track for Q3 FY26 for GA of WXCC-10116 (Analyzer Reports for QM) | Clarity on requirements
Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | Enhance reporting & analytics for AI products including ROI | 2026-05-12 06:48 | Month 1 | May 19 (Q3 QBR) | Off Track/Delayed | 2 feature | - Reporting for AI QM - Human Agent reports in Analyzer next month. For AI Agents planned for July. - Reporting for AI Assistant - Delayed to Q1/Q2FY27 due to prioritizing AI Assistant Get Well Plan. - Reporting for AI WFM - In Planning. Planned for Q1FY27 - Analyzer feature - Comprehensive Home page on track for July GA. - Analyzer feature - Streamlined create visualization - July end Beta. GA will be delayed to Q1FY27. | Clarity on requirements
Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | Enhance reporting & analytics for AI products including ROI | 2026-05-27 12:16 | Month 2 | Jun 4 (June MBR) | Off Track/Delayed | 0 features | - Reporting for AI QM - Human Agent reports in Analyzer will be in June. For AI Agents planned for July beta. - Reporting for AI Assistant - Delayed to Q1/Q2FY27 due to prioritizing AI Assistant Get Well Plan. - Reporting for AI WFM - In Planning. Planned for Q1FY27 - Analyzer feature - Comprehensive Home page on track for July GA. - Analyzer feature - Streamlined create visualization - August/Sept beta. GA will be delayed to Q1FY27. | Clarity on requirements
Enable the field and partners to confidently sell AI | AI Cookbooks | 2026-02-09 05:00 |  | Feb 6 (February MBR) | Planning
Enable the field and partners to confidently sell AI | AI Cookbooks | 2026-05-12 15:09 | Month 1 | May 19 (Q3 QBR) | On Track | Cookbook complete, pending review before publishing it. | The AI Cookbook is finalized and currently undergoing internal review. Once approved, this resource will be published externally to provide partners with actionable guidance on best practices and, accelerating AI deployment], directly supporting our cloud adoption goals.
Enable the field and partners to confidently sell AI | AI Cookbooks | 2026-06-02 20:33 | Month 2 | Jun 4 (June MBR) | On Track |  | CookBook will be made public on Jun 5th
Enable the field and partners to confidently sell AI | Establish AI demo enablement and availability | 2026-02-09 05:00 |  | Feb 6 (February MBR) | On Track |  | Demo Library is active, but need to discuss with Jitesh on when to transition this over to his team.
Enable the field and partners to confidently sell AI | Establish AI demo enablement and availability | 2026-05-13 01:58 | Month 1 | May 19 (Q3 QBR) | On Track | Demo Library is active, but need to discuss with Jitesh on when to transition this over to his team. | Demo Library is active, but need to discuss with Jitesh on when to transition this over to his team.
Enable the field and partners to confidently sell AI | Expand the AI use-case library by vertical and whitespace | 2026-02-09 05:00 |  | Feb 6 (February MBR) | On Track |  | Usecase Library is active and currently at 60+ usecases.
Enable the field and partners to confidently sell AI | Expand the AI use-case library by vertical and whitespace | 2026-05-08 03:28 | Month 1 | May 19 (Q3 QBR) | On Track | 100% of live use cases are now documented and accessible to internal resources. | - Scaled to 71 published use cases FTD (+11 this period). - Healthcare expansion will utilize our existing, validated deployment model to accelerate time-to-market.
Enable the field and partners to confidently sell AI | Internal AI Evangelization | 2026-02-09 05:00 |  | Feb 6 (February MBR) | On Track |  | Chandra is working with Zack to get the Experts call to become the standing call for AI Experts, rather than the standalone call that happens today.
Enable the field and partners to confidently sell AI | Internal AI Evangelization | 2026-05-12 15:18 | Month 1 | May 19 (Q3 QBR) | On Track | Established recurring 30-minute monthly AI enablement session within the WebEx Experts call. | Successfully partnered with Product Management to secure a standing monthly slot on the WebEx Experts call. This provides a dedicated, scalable channel to evangelize AI capabilities to Sales, Solutions Engineers, and cross-functional teams, ensuring consistent messaging and technical readiness across the field.
Enable the field and partners to confidently sell AI | MCP Factory | 2026-02-09 05:00 |  | Feb 6 (February MBR) | On Track
Enable the field and partners to confidently sell AI | MCP Factory | 2026-05-08 03:43 | Month 1 | May 19 (Q3 QBR) | On Track | 11 | Launched the MCP Factory within the AI Customer Hub, delivering 11 MCP servers in Q3 (exceeding the target of 5). This framework enables secure, autonomous integrations for Athena, Salesforce, and ServiceNow, streamlining field deployment of AI agents.
Enable the field and partners to confidently sell AI | New Product References | 2026-02-09 05:00 |  | Feb 6 (February MBR) | On Track |  | 3 customers for AI QM and 2 for AI Routing are under trial, and 1 customer underway for MCP/A2A
Enable the field and partners to confidently sell AI | New Product References | 2026-05-08 03:31 | Month 1 | May 19 (Q3 QBR) | On Track | - 3 AI QM references. - 2 A2A/MCP references. | Secured 5 new product references (3 AI QM, 2 A2A/MCP).
Enable the field and partners to confidently sell AI | Public AI customer endorsemenets | 2026-02-09 05:00 |  | Feb 6 (February MBR) | On Track |  | Multiple customers went live: Seminole Hardrock, Missippi Gulf Coast. Marketing team is also working on case studies, we had the Uniting webinar publicly published in Feb.
Enable the field and partners to confidently sell AI | Public AI customer endorsemenets | 2026-05-08 03:34 | Month 1 | May 19 (Q3 QBR) | On Track | Published 11 public AI customer references in Q3 | Published 11 public AI customer references in Q3, now fully available to support internal field teams and accelerate AI adoption.
Enable the field and partners to confidently sell AI | Verticalised approach and focus for AI | 2026-02-09 05:00 |  | Feb 6 (February MBR) | On Track |  | Plan is in place and working through with the team: <https://cisco.sharepoint.com/sites/WebexCXAI/SitePages/Epic-Usecases-Methodology.aspx>
Enable the field and partners to confidently sell AI | Verticalised approach and focus for AI | 2026-03-31 19:56 |  | Apr 7 (April MBR) | On Track | - Healthcare: Team delivered 4 use cases, including customer documentation and partner documentation. This includes Epic and Athena (2nd in market share). Marketing slides were delivered. - Working on getting into the Athena marketspace. |  | Epic continues to be challenging. Looking into 3rd party assistance through Nordic (https://nordicglobal.com)
Enable the field and partners to confidently sell AI | Verticalised approach and focus for AI | 2026-05-06 22:01 | Month 1 | May 19 (Q3 QBR) | On Track | To accelerate our verticalized strategy, we have selected InterSystems as our strategic partner to provide the HL7 gateway, a critical foundation for unlocking our AI-driven healthcare use cases. | By securing full alignment with the Product Management team, we have validated our technical roadmap and confirmed our path forward. We are now finalizing the Statement of Work, setting the stage to transition this initiative into active execution. | Epic continues to be difficult to engage.
Make AI easy to start and hard to abandon | Define and operationalize in-life AI adoption motions | 2026-01-09 05:00 |  | Jan 8 (January MBR) | Planning
Make AI easy to start and hard to abandon | Define and operationalize in-life AI adoption motions | 2026-02-09 05:00 |  | Feb 6 (February MBR) | Planning |  | - Analysing DV's Airtable to adapt into a whitespace grid. Working with Dave Jennings to explore incorporating use-cases into CoE discovery tool - ROI data gathering requirements being pushed to CSMs to update into Airtable.
Make AI easy to start and hard to abandon | Define and operationalize in-life AI adoption motions | 2026-04-01 15:55 |  | Apr 7 (April MBR) | On Track |  | Continuing work with DV's Customer Hub Airtable to turn into whitespace/use case library.
Make AI easy to start and hard to abandon | Define and operationalize in-life AI adoption motions | 2026-04-20 12:52 |  | May 19 (Q3 QBR) | On Track | ROI being collected where available - need to find a way with Dave Veevers on aggregating and making it reportable | - Use case library: <https://airtable.com/appUJj24OxwiVXkGr/pag6EmPvdibW1rELf> (16 use cases) - Customer/sector use cases: https://airtable.com/appUJj24OxwiVXkGr/pagZ6G30hwZKJ4TaI?aojWI=allRecords | No automation and aggregation of ROI data into a dashboard. Very manual CSM/SCG team exercise to collate ROI stats.
Make AI easy to start and hard to abandon | Dog and Pony Show | 2026-02-09 05:00 |  | Feb 6 (February MBR) | Planning
Make AI easy to start and hard to abandon | Dog and Pony Show | 2026-05-13 17:09 | Month 1 | May 19 (Q3 QBR) | Planning | N/A | We are actively collaborating with the Collaboration GTM leadership to transition this framework into their portfolio, ensuring long-term scalability and seamless integration into our broader go-to-market strategy.
Make AI easy to start and hard to abandon | Dog and Pony Show | 2026-05-31 18:44 | Month 2 | Jun 4 (June MBR) | At Risk | Met with the account teams for all target GES opportunities and segmented them based on relationship and investment. SCG and COW are engaged in the investment accounts, but executive / GTM involvement is required in the majority of GES accounts to rebuild the relationship and capture mindshare.
Make AI easy to start and hard to abandon | Publish Re-usable AI Agents | 2026-02-09 05:00 |  | Feb 6 (February MBR) | Planning
Make AI easy to start and hard to abandon | Publish Re-usable AI Agents | 2026-05-12 15:19 | Month 1 | May 19 (Q3 QBR) | Off Track/Delayed | Two re-usable AI Agent templates published. | While we successfully deployed two templates this quarter, progress was paced by a dependency on the AI Cookbook. With the Cookbook now finalized, we have cleared the primary blocker and are positioned to accelerate the development and release of the remaining templates in the coming period.
Scale AI across platform and ecosystem | AI deployment/activation plan (FDE Model) | 2026-01-09 05:00 |  | Jan 8 (January MBR) | Planning | N/A | Given the recent org changes, need to align with Prakash, Abhiram and Vinod on this Sub-Method and measure. BU will not deliver services.
Scale AI across platform and ecosystem | AI deployment/activation plan (FDE Model) | 2026-02-09 05:00 |  | Feb 6 (February MBR) | Off Track/Delayed | N/A | There will not be a SKU. Arvind to confirm with Vinod on this sub-method given the recent org changes.
Scale AI across platform and ecosystem | AI deployment/activation plan (FDE Model) | 2026-04-10 16:28 |  | Apr 7 (April MBR) | Planning | TBD | This method needs to be discussed with Vinod and perhaps re-purpose it given the new direction of creating a FDE team (Foward deployed Engineer) for help accelerate AI use cases, value realization and implementation.
Scale AI across platform and ecosystem | AI deployment/activation plan (FDE Model) | 2026-05-13 17:05 | Month 1 | May 19 (Q3 QBR) | Planning | N/A | Operationalized the FDE model in BETA phase as of Q3, establishing a strategic framework to accelerate AI adoption and usage revenue.
Scale AI across platform and ecosystem | Execute third-party AI POCs where strategically required | 2026-02-09 05:00 |  | Feb 6 (February MBR) | On Track |  | We had meetings for Neural Fabric with NYU Langone and for Ez Dubz with about 5 customers, on track and progressing.
Scale AI across platform and ecosystem | Execute third-party AI POCs where strategically required | 2026-05-07 16:14 | Month 1 | May 19 (Q3 QBR) | On Track | Successfully conducted the US Innovation Council meeting, maintaining an average attendance of 25–30 participants from a core group of 55 customer members. | The Innovation Council continues to serve as a high-value feedback loop, enabling our Product Management teams to rigorously vet product viability and roadmap alignment. Participants have expressed strong appreciation for the opportunity to directly influence our product backlog and feature prioritization. Given this positive engagement, we are currently planning to scale this model into additional geographies by the end of the fiscal year to broaden our global customer perspective.
Scale AI across platform and ecosystem | Launch AI-specific One Cisco GTM initiatives | 2026-02-09 05:00 |  | Feb 6 (February MBR) | Planning
Scale AI across platform and ecosystem | Launch AI-specific One Cisco GTM initiatives | 2026-05-13 02:03 | Month 1 | May 19 (Q3 QBR) | On Track | 5 active POCs with EzDubs. | We have successfully scaled our engagement with EzDubs, currently managing five active POCs that are demonstrating strong potential for enterprise outcomes. Regarding the Neuralfabric target, we conducted a strategic assessment and determined that this integration does not align with our current FY26 deliverables; consequently, we have deprioritized this effort to focus resources on higher-impact opportunities.

## Airtable Record Comments
Record Type | Top-Level Method | Sub-Method | Comment Date | Author | Comment
No Airtable record comments found