## Overview
All H2 Values - Methods and Comments
Report Summary | Value
Base | CX FY26 V2MOM - NEW
Source | Live Airtable MCP
Template | All H2 Values - Methods and Comments
Reporting Period Filter | Jun 4 (June MBR)
H2 Values Included | 8
Top-Level Method Rows | 22
Sub-Method Rows | 58
Dated Top-Level Update Rows | 27
Dated Sub-Method Update Rows | 60
Airtable Record Comments | 0
Extraction Note | Reporting-period extract using the standard all-H2 methods/comments workbook structure.
H2 Value Summary
H2 Order | H2 Value | Group | Team | Top-Level Methods | Sub-Methods | TL Updates | SM Updates | Record Comments
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | GTM; Customer Success; Solutioning | Technical Solution and Onboarding | 2 | 9 | 3 | 9 | 0
2 | Win Greenfield, Enterprise Contact Center Customers | GTM; Customer Success; Solutioning | Customer Success | 3 | 8 | 4 | 8 | 0
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Marketing | Strategic Messaging & Communications | 5 | 10 | 7 | 12 | 0
4 | Accelerate AI Growth and Adoption | Product Management | On Prem Product Management | 3 | 4 | 4 | 4 | 0
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | 5 | 22 | 5 | 22 | 0
6 | Strengthen Market Positioning and Routes to Market | GTM; Customer Success; Solutioning | GTM | 1 | 2 | 1 | 2 | 0
7 | Other | GTM; Customer Success; Solutioning | GTM | 3 | 2 | 3 | 2 | 0
| Not linked in Airtable |  |  | 0 | 1 | 0 | 1 | 0

## Top-Level Methods
H2 Order | H2 Value | Group | Team | Top-Level Method | Method Owner Name | Status Owner | Method Team | Measure Description | FY26 Measure | Current Status | Current Actual | Current Commentary | Previous Status | Previous Actual | Previous Commentary | Status Update Date | Reporting Period | Sub-Method Count | Dated Update Count
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | GTM; Customer Success; Solutioning | Technical Solution and Onboarding | Execute disciplined migration from on-prem to Webex Contact Center | Karthik Sundaram | Maurice Lopes | Technical Solutioning | % of Available to Renew On-Prem seats migrated to Cloud | 13% (49k from 385k ATR) | At Risk | 3.7% (1.0K / 27K) | Migration to the cloud is behind plan due to restrictive CCX offer criteria (75% of deals fail to qualify for the migration tool) and a lack of CCE-to-WxCC migration tool or incentives. The Collaboration GTM is currently revamping commercial offers to improve the value proposition and accelerate cloud adoption. |  |  |  | 2026-06-03 12:05 | Jun 4 (June MBR) | 4 | 1
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | GTM; Customer Success; Solutioning | Technical Solution and Onboarding | Protect and grow renewal revenue in the installed base | Jitesh Gera | Not specified | Offers | % of Available to Renew On-Prem seats renewed # of total billed CCX/CCE On-Prem seats | - 73% of ATR On-Prem seats renewed - Maintain 921k seats | At Risk | 54% renewed from Q4M1 ATR (14.8k from 27.4k) 902.7k seats | 42% of Q4 ATR renewed, 13% lost, 6% downsell, 42% still available to be renewed. |  |  |  | 2026-06-03 12:08 | Jun 4 (June MBR) | 7 | 2
2 | Win Greenfield, Enterprise Contact Center Customers | GTM; Customer Success; Solutioning | Customer Success | Deliver product features specifically blocking large, impactful enterprise deals | Chang Chang | Nikki Heyder | Cloud Product Management | Number of features delivered | 2 per quarter | On Track | 2 in progress | See commentary below |  |  |  | 2026-06-11 16:44 | Jun 4 (June MBR) | 1 | 1
2 | Win Greenfield, Enterprise Contact Center Customers | GTM; Customer Success; Solutioning | Customer Success | Expand enterprise demand through adjacency and One Cisco motions | Helen Briggs | Not specified | Collab GTM | Leverage the power of One Cisco | Increase in no of opportunities in pipeline from customers who bought other Cisco franchises | On Track | 5/12 - FY27 plan should be finalised followng this weeks meetings in NY | 5/12 - FY27 Collaboration Product GTM plan focuses on 3 pillars: 1. AI Attach 2. Grow Devices business by 100% 3. Foundational |  |  |  | 2026-05-12 11:04 | Jun 4 (June MBR) | 6 | 1
2 | Win Greenfield, Enterprise Contact Center Customers | GTM; Customer Success; Solutioning | Customer Success | Unblock enterprise deals through product and pricing | Helen Briggs | Not specified | Collab GTM | # of Webex CC deals with >1000 seats # of greenfield Webex Contact Center seats (booked seats classified ‘New to Contact Center’ including bookings for customers without bookings/AOV for ‘Contact Center’ SBE in the last 3 years) | 10 deals > 1k seats 40k Greenfield seats | At Risk | 2 deals >= 1k seats 1.3K greenfield seats | 2 deals, DSV & MakeMyTrip booked 10,00 seats in M9. |  |  |  | 2026-06-03 12:12 | Jun 4 (June MBR) | 4 | 2
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Marketing | Strategic Messaging & Communications | Drive expansion of Webex Contact Center | Tristan Jewitt | Kamesh Chidambaram | Customer Success | Number of WxCC/AI opportunities raised by CSM team Number of CPaaS opportunities raised by CSM team | - 100 WxCC/AI opportunities raised - 200 CPaaS opportunities raised | At Risk | 2 WxCC opportunities | Only 2 opportunities raised so far against target of 25 in Q4. However, we exceeded target in Q3 at 35. |  |  |  | 2026-06-03 02:12 | Jun 4 (June MBR) | 2 | 1
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Marketing | Strategic Messaging & Communications | Drive post-sale adoption as a core operating motion | Tristan Jewitt | Kamesh Chidambaram | Customer Success | Reduction of zero-usage Cloud customers from Q4FY25 of 9% (125 customers) | 25% reduction | On Track | 86 Accounts | No usage tenants count stands at 86 tenants (6%), compared to 106 tenants (7%) at end Q3​ |  |  |  | 2026-06-09 09:33 | Jun 4 (June MBR) | 4 | 1
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Marketing | Strategic Messaging & Communications | Improve CX renewal rates and contract duration | Tristan Jewitt | Not specified | Sales-COE | 90% Renewal rate - WxCC | 34k WxCC Seats renewed | On Track | ​Q4 WxCC renewal is currently at 48.0% | ​Q4 WxCC renewal is currently at 48.0%, with 3,740 of 7,785 scoped seats renewed. The largest opportunity is the remaining renewal base: 2,871 seats across 101 accounts, representing $2.66M AOV still up for renewal. |  |  |  | 2026-06-03 02:10 | Jun 4 (June MBR) | 5 | 1
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Marketing | Strategic Messaging & Communications | Maintain product quality and availability | Ravi Kiran Vadlamani | Betty Mai | Engineering | Ensures consistent product quality, availability and reliability across all platforms | Breakdown is identified at submethod level. | At Risk | WxCCE: May Platform Availability - 99.819%, May 2026 Overall Availability - 99.986%, 0 CAP / 0 Hot WxCC: May Global 99.995% CPaaS: May 100% Platform Availability | Availability for WxCCE in May 2026 showed platform availability at 99.819% and overall availability at 99.986%, impacted by data center outages in Almere and Denver affecting some customers geographically. There were 33 customer escalations, with five customers experiencing SLA-impacting issues: Propharma, Tesco, Capgemini, Portland General Electric, and Kaiser Permanente NCS. WxCC recorded a global availability of 99.995%, though impacted by two P1 incidents affecting the US Prod1 environment. CPaaS maintained 100% platform availability despite experiencing two channel-impacting incidents related to RCS delivery in the US AWS and Azure environments. |  |  |  | 2026-06-10 15:46 | Jun 4 (June MBR) | 4 | 3
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Marketing | Strategic Messaging & Communications | Reduce operational friction through in-life automation | Martin King | Not specified | Help Desk & Solution Management | % of cases raised to CX Helpdesk resolved automatically |  | At Risk | 72.4% | Need for Human support rate increased due to high failure rates on Webex Campaign and Notify |  |  |  | 2026-06-04 10:31 | Jun 4 (June MBR) | 2 | 1
4 | Accelerate AI Growth and Adoption | Product Management | On Prem Product Management | Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | Chang Chang | Manali Dongre | Cloud Product Management | Number of capabilities enabled | **8 capabilities (rollup of sub measures)** | Off Track/Delayed | 1.5 | Reporting for AI QM - Human Agent reports in Analyzer will be in June. For AI Agents planned for July beta. Reporting for AI Assistant - Delayed to Q1/Q2FY27 due to prioritizing AI Assistant Get Well Plan. Reporting for AI WFM - In Planning. Planned for Q1FY27 Analyzer feature - Comprehensive Home page on track for July GA. Analyzer feature - Streamlined create visualization - August/Sept beta. GA will be delayed to Q1FY27. AI Assistant delivered in PowerBI |  |  |  | 2026-06-11 16:16 | Jun 4 (June MBR) | 4 | 1
4 | Accelerate AI Growth and Adoption | Product Management | On Prem Product Management | Enable the field and partners to confidently sell AI | Abhiram Kramadhati | Not specified | AI Solution Consulting Group | Published customer references or completed events for CX AI products | 20 references/events | On Track | 78 usecases published to the usecase library. | 78 usecases published to the usecase library. Many of these are in the pipeline to become externally referencable. |  |  |  | 2026-06-11 11:13 | Jun 4 (June MBR) | 8 | 1
4 | Accelerate AI Growth and Adoption | Product Management | On Prem Product Management | Make AI easy to start and hard to abandon | Abhiram Kramadhati | Maurice Lopes | Sales-COE | % attach rate for AI Agent & Assistant (against total billed WxCC customers) | - AI Agent - 20% attach - AI Assistant - 10% attach | At Risk | WxCC Installed base: \- AI Agent: 10% \- AI Assistant: 10% \- Overall Attach: 13% New orders: \- AI Agent: 20% \- AI Assistant: 13% \- Overall Attach: 24% | For Q4, we are manually reaching out to the RMs to drive attach - atleast uncommitted so that the activation is done. By end of Q4, we will report on uncommitted attach as well because that is an important metric - they are not being reflected today. |  |  |  | 2026-06-11 11:15 | Jun 4 (June MBR) | 7 | 2
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Context driven orchestration | Chang Chang | Kavyanidhi Narayan | Cloud Product Management | Number of capabilities/services enabled | 12 features including GA and Beta | Off Track/Delayed | 0 | See specific comments below |  |  |  | 2026-06-11 16:32 | Jun 4 (June MBR) | 4 | 1
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Extensible AI native platform | Chang Chang | Kavyanidhi Narayan | Cloud Product Management | Number of features delivered | 37 features GA 6 workloads (MVO in Beta) 3 features Beta (WFM) 2 use cases (tentative) | Off Track/Delayed | 12 | See specific commentary below |  |  |  | 2026-06-11 16:21 | Jun 4 (June MBR) | 11 | 1
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Intelligent front door | Chang Chang | Kavyanidhi Narayan | Cloud Product Management | Number of features/capabilities/services enabled | 36 GA features, 1 S2S Engine in Beta, 3 technology previews | Off Track/Delayed | 0 | See specific commentary below |  |  |  | 2026-06-11 16:23 | Jun 4 (June MBR) | 4 | 1
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Trusted & Secure by design | Chang Chang | Kavyanidhi Narayan | Cloud Product Management | Number of impactful On Cisco use cases delivered | 5 GA features + 7 use cases (this count includes both On-Prem and Cloud CX Products) | At Risk | 2 in progress | AI Defense update captured in AI Studio update, other features on track |  |  |  | 2026-06-11 17:24 | Jun 4 (June MBR) | 2 | 1
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Unlock team potential and development excellence | Ravi Kiran Vadlamani | Betty Mai | Engineering | Optimize development through standardized media infrastructure and AI-driven workflows to double capacity and halve delivery timelines. |  | On Track | See below for current actuals | Engineering initiatives are showing strong progress, with the SDLC acceleration effort successfully meeting its goal of cutting feature delivery time by over 50% (from 279 to 130 days). AI integration is driving significant efficiency, evidenced by 86% of WxCC/CCE code PRs utilizing GenAI and CPaaS teams achieving a 50% increase in delivery capacity. Simultaneously, media convergence development has officially kicked off, remaining on track for a target GA in FY27Q3. |  |  |  | 2026-06-11 22:26 | Jun 4 (June MBR) | 5 | 1
6 | Strengthen Market Positioning and Routes to Market | GTM; Customer Success; Solutioning | GTM | Establish new and expand existing strategic technology partnerships | Tom Clifford | Not specified | Collab GTM | Strategic partnerships identified and/or announced | - Salesforce SCV/BYO CCaaS announce - SNOW Integration/MCP announce - Knowledge & Search platforms identified | On Track | On Track | Taking slightly longer to implement than expected but no particular blockers, should be complete by end of June |  |  |  | 2026-06-08 08:00 | Jun 4 (June MBR) | 3 | 1
7 | Other | GTM; Customer Success; Solutioning | GTM | Address billing issues and reduce unbilled revenue | Nir Feldberg | Not specified | Customer Success | Have no customers with unbilled revenue for 3 consective months | <3 consecutive months on unbilled revenue list | On Track | April total = $2.59M Resolved = $1.15M New May = $1.89M May Total = $3.33M | Backlog improved but new may drove the increase |  |  |  | 2026-06-08 08:11 | Jun 4 (June MBR) | 1 | 1
7 | Other | GTM; Customer Success; Solutioning | GTM | Grow the Cloud Contact Center business | Vinod Muthukrishnan | Jason Wemyss |  | # of Webex Contact Center Agents by end of FY26 | 250K seats | Off Track/Delayed | Q4M1 Close - 185k seats |  |  |  |  | 2026-06-03 12:16 | Jun 4 (June MBR) |  | 1
7 | Other | GTM; Customer Success; Solutioning | GTM | Retain CPaaS run rate business | Nir Feldberg | Tristan Jewitt | CPaaS | Revenue growth and retention rate of >$100k customers | - 105% revenue growth existing customers - 95% retention >$100k customers | On Track | •108% revenue growth existing customers •100% retention >$100k customers | On track to exceed the 105% revenue growth target |  |  |  | 2026-06-09 10:49 | Jun 4 (June MBR) | 1 | 1

## Sub-Methods
H2 Order | H2 Value | Group | Team | Top-Level Method | Sub-Method | Owner - Supporting Method | Status Owner | Sub-Method Team | Measure Description | FY26 Measure | Current Status | Current Actual | Current Commentary | Previous Status | Previous Actual | Previous Commentary | Status Update Date | Reporting Period | Dated Update Count | FIRA Count | FIRAs | FIRA Feature Names | FIRA Latest Release Quarter Status | FIRA JIRA Status | FIRA JIRA Feature State | FIRA Latest Update Quarter | FIRA Market Access | FIRA CLUS Payload Items | FIRA CLUS Payload Items NEW
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | GTM; Customer Success; Solutioning | Technical Solution and Onboarding | Execute disciplined migration from on-prem to Webex Contact Center | Migrate CCE customers to Webex Contact Center using defined offers and tooling | Karthik Sundaram | Melissa Riner | Technical Solutioning | # of CCE seats migrated to WxCC | 23k seats | Off Track/Delayed | 1410 | Our cloud migration for renewed seats is currently tracking behind schedule. This is primarily driven by the lack of a CCE to WxCC migration tool and associated incentives. To address this challenge and accelerate cloud adoption, the Collaboration GTM team is evaluating our existing commercial offers and revamping our incentives to create a more compelling value proposition for our customers. Additionally, our vendor, Univnoix, is currently assessing the effort required to build a dedicated migration tool for CCE to WxCC. |  |  |  | 2026-06-09 15:54 | Jun 4 (June MBR) | 1
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | GTM; Customer Success; Solutioning | Technical Solution and Onboarding | Execute disciplined migration from on-prem to Webex Contact Center | Migrate CCX customers to Webex Contact Center through partner-led motions | Karthik Sundaram | Melissa Riner | Technical Solutioning | # of CCX seats migrated to WxCC # of migrations leveraging migration tool # of partners leveraging migration program offer | 31k seats | Off Track/Delayed | 758 | City of Boston is first customer to go live with migration tool. The current migration offer is not achieving the intended outcomes. Until the GTM strategy and offer are updated, we anticipate continued challenges in driving improved results. |  |  |  | 2026-06-09 15:49 | Jun 4 (June MBR) | 1
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | GTM; Customer Success; Solutioning | Technical Solution and Onboarding | Modernize the on-prem base through AI innovation | AI Assistant features | Girish Variyath | Girish Variyath | On Prem Product Management | Availability of AI Assistant features | GA AI Assistant: AI Agent Summary (Voice) Realtime Transcript (Voice) Realtime Assist (Voice) Wrap-up Summary (Voice) | At Risk | Beta in progress. | GA in Q4 at risk due to lack of support from billing and offers team |  |  |  | 2026-06-10 13:13 | Jun 4 (June MBR) | 1 | 4
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | GTM; Customer Success; Solutioning | Technical Solution and Onboarding | Modernize the on-prem base through AI innovation | Customer trials of AI Assistant features | Girish Variyath | Girish Variyath | On Prem Product Management | Customer trials of AI Assistant features | Beta AI Assistant: AI Agent Summary (Voice) Realtime Transcript (Voice) Realtime Assist (Voice) Wrap-up Summary (Voice) | On Track | Beta in progress | Beta customers: Nat Grid, FNB, Autozone, Lowes, Staples, MGB, B+S |  |  |  | 2026-06-10 13:15 | Jun 4 (June MBR) | 1 | 4
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | GTM; Customer Success; Solutioning | Technical Solution and Onboarding | Modernize the on-prem base through AI innovation | Deliver CCE on-prem sovereign solutions | Girish Variyath | Girish Variyath | On Prem Product Management | Release BYOVA / BYOAI solutions for sovereign customers/partners, using Fusion (UH on-prem) | GA AI Fusion | At Risk | Beta in progress at T Mobile and started at Bajaj Finance Limited | PM role eliminated |  |  |  | 2026-06-10 13:11 | Jun 4 (June MBR) | 1 | 1
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | GTM; Customer Success; Solutioning | Technical Solution and Onboarding | Modernize the on-prem base through AI innovation | Nutanix hypervisor support for CCE | Girish Variyath | Girish Variyath | On Prem Product Management | Provide alternate hypervisor options to customers who want to exit VMWare. Support on Cisco HCI servers with 3-node solution | GA Nutanix hypervisor support on Cisco HCI for UCCE and PCCE(4K and higher) | On Track | GA on track - planned for end Q4FY26 | Beta in progress: HCSC, T-Mobile, Keck |  |  |  | 2026-06-10 08:56 | Jun 4 (June MBR) | 1 | 1
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | GTM; Customer Success; Solutioning | Technical Solution and Onboarding | Modernize the on-prem base through AI innovation | Nutanix hypervisor support for PCCE 2K | Girish Variyath | Girish Variyath | On Prem Product Management | Nutanix hypervisor support for PCCE 2K | GA Nutanix hypervisor support for PCCE 2K | On Track | Plan for GA in Q4FY26 | Also adds support for single-node hypervisor deployment |  |  |  | 2026-06-10 13:25 | Jun 4 (June MBR) | 1 | 1
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | GTM; Customer Success; Solutioning | Technical Solution and Onboarding | Protect and grow renewal revenue in the installed base | Accelerate cloud migrations (401K) | Karthik Sundaram | Melissa Riner | Technical Solutioning | # of on-prem seats (CCX + CCE) migrated to WxCC | 54K seats | Off Track/Delayed | 2168 | Migration to the cloud is behind plan due to restrictive CCX offer criteria (75% of deals fail to qualify for the migration tool) and a lack of CCE-to-WxCC migration tool or incentives. The Collaboration GTM is currently revamping commercial offers to improve the value proposition and accelerate cloud adoption. |  |  |  | 2026-06-09 15:41 | Jun 4 (June MBR) | 1
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | GTM; Customer Success; Solutioning | Technical Solution and Onboarding | Protect and grow renewal revenue in the installed base | Incentivise and upgrade CCX base to R15.0 | Karthik Sundaram | Maurice Lopes | Technical Solutioning | # of CCX customers upgraded to R15 | TBD | Planning | N/A | We are partnering with IT and Webex Analytics to build a dedicated dashboard for on-prem R15 upgrades. This tool will utilize smart licensing data to resolve current visibility gaps and allow for clear segmentation between UCCX and UCCE. |  |  |  | 2026-06-09 15:43 | Jun 4 (June MBR) | 1
2 | Win Greenfield, Enterprise Contact Center Customers | GTM; Customer Success; Solutioning | Customer Success | Deliver product features specifically blocking large, impactful enterprise deals | Deliver approved critical customer commits | Nikki Heyder | Nikki Heyder | Cloud Product Management | Number of features delivered | 2 per quarter | On Track | 2 features | 2 features delivered (Extended Email Search History (Aviva) and ability to provision contact center through wholesale. with 8 items currently in development - including features like Generic Task Routing (Pacifica), Background Noise Suppression ifor WebRTC (Lee Health), In App 'Live Chat SDK' support (Health Equity), BYOC (Cisco IT) and Analyzer Unified Reporting (WxCC & WxC) (Polyexpert) |  |  |  | 2026-06-11 16:35 | Jun 4 (June MBR) | 1
2 | Win Greenfield, Enterprise Contact Center Customers | GTM; Customer Success; Solutioning | Customer Success | Expand enterprise demand through adjacency and One Cisco motions | Align marketing, sales, product, and partner orgs on vertical campaigns, messaging, content and targeted account lists - WxCC and AI | Helen Briggs | Not specified | Collab GTM | Move away from silo'd teams supporting random initiatives | One plan that each of the key stakeholders in Sales, Product, Partners and marketing support | On Track | 5/12 - FY27 priorities being finalised this week in NY | 5/12 - H2 bridge plans in execution and FY27 priorities aligning key stakeholders in sales, partners, marketing progressing very well. |  |  |  | 2026-05-12 11:00 | Jun 4 (June MBR) | 1
2 | Win Greenfield, Enterprise Contact Center Customers | GTM; Customer Success; Solutioning | Customer Success | Expand enterprise demand through adjacency and One Cisco motions | Create One Cisco enterprise CX programs (including EA-based offers) | Tim Hoolihan | Kevin McPartlan | Collab GTM | Stop building individual CX pricing constructs and build align into EA 3.0 | Get all CX offers in EA 3.0 | On Track | 5/12 - tied to overall Collaboration procing strategy work that Tim H and team are driving | 5/12 - looking to build offers to fit into existing buying models that are favourable with enterprise customers, eg EA3.0 |  |  |  | 2026-05-12 11:02 | Jun 4 (June MBR) | 1
2 | Win Greenfield, Enterprise Contact Center Customers | GTM; Customer Success; Solutioning | Customer Success | Expand enterprise demand through adjacency and One Cisco motions | Launch sales plays for Cisco Calling customers | Charlotte Jewsbury | Not specified | Collab GTM | Increase in WxCC attach to Webex Calling customer base | TBC | On Track |  | 1) kicked off activity with renewal team for opps to end FY27 >$50k AOV (approx 220 customers), any leads will be passed to CX specialists 2) finalised target list for FY28+ customers (approx 1400), kicked off work with Marketing to review list for outbound marketing activity - awaiting output & timeline |  |  |  | 2026-06-01 11:31 | Jun 4 (June MBR) | 1
2 | Win Greenfield, Enterprise Contact Center Customers | GTM; Customer Success; Solutioning | Customer Success | Expand enterprise demand through adjacency and One Cisco motions | Leverage Cisco’s broader installed base (networking, security, collaboration) to open CX doors. | Helen Briggs | Not specified | Collab GTM | Leverage the power of One Cisco | Increase in no of opportunities in pipeline from customers who bought other Cisco franchises | On Track | 5/12 - Continued in progress | 5/12 - This is ongoing throughout the year - John Kiang and team continue to help identify which customers by SL1, SL2, SL3 ahave recently bought large networking, security, collaboration deals that may help sales engage and upsell CX. |  |  |  | 2026-05-25 11:07 | Jun 4 (June MBR) | 1
2 | Win Greenfield, Enterprise Contact Center Customers | GTM; Customer Success; Solutioning | Customer Success | Unblock enterprise deals through product and pricing | Competitive takeout campaigns (e.g. Avaya, Genesys) | Jitesh Gera | Not specified | Collab GTM | # #of deals and booking value from competitive takeout wins | Launch Genesys Prog and win min 1 deal by end FY26 | On Track | 5/12 - Genesys Top 50 progressing. | 5/12 - Team cleaning data (CAV BU name vs SAV name) so that SFDC and Gong tracking can be done. GTM team cooordinating with SDR, as they have already been collaborating with an external agency to reach out to specific accounts. There was an ask to support a light touch approach on Five9s GES and large commercial customers but recent earnings were more positive than expected, so this is being de prioritised in Q4. |  |  |  | 2026-05-12 10:46 | Jun 4 (June MBR) | 1
2 | Win Greenfield, Enterprise Contact Center Customers | GTM; Customer Success; Solutioning | Customer Success | Unblock enterprise deals through product and pricing | Deliver offers from product features that unblock enterprise deals | Tim Hoolihan | Kevin McPartlan | Collab GTM | Ensure all new product SKUs for new features, capabilities, products are available on GPL | Launch all new GA product SKUs on GPL | On Track | 5/12 - Product and GTM teams aligned, relevant offer go live plans in progress | 5/12 - No Q4 deal is blocked due to delayed offer availability |  |  |  | 2026-05-12 10:49 | Jun 4 (June MBR) | 1
2 | Win Greenfield, Enterprise Contact Center Customers | GTM; Customer Success; Solutioning | Customer Success | Unblock enterprise deals through product and pricing | Develop strategic portfolio pricing aligned to enterprise buying models | Tim Hoolihan | Kevin McPartlan | Collab GTM | Stop building silo'd pricing strategies by product/BU and start building Collaboration wide buying modeld that new SKUs align to | Deliver strategic portfolio pricing model for all of Collaboration | On Track | 5/12 - Tim Hoolihan successfully pivoting the teams to leverage customer preferred buying models | 5/12 - Offer team revising pricing strategies, moving away from BU silo'd approaches, to one that leverages EA3.0 and will build new offers to fit these customer preferred buying models |  |  |  | 2026-05-12 10:51 | Jun 4 (June MBR) | 1
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Marketing | Strategic Messaging & Communications | Drive post-sale adoption as a core operating motion | Define and execute structured in-life adoption motions | Kamesh Chidambaram | Shreya Srinivas | Customer Success | Launch automated digital comms program | 90% Coverage for customer outreach program | At Risk | No change in customer coverage - 74% of all tech touch customers. New customer track yet to start. | Second email campaign delayed due to impacts to Marketing team. New date TBD. |  |  |  | 2026-06-02 11:34 | Jun 4 (June MBR) | 1
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Marketing | Strategic Messaging & Communications | Drive post-sale adoption as a core operating motion | Document and replicate successful expansion blueprints (white glove, events, executive engagement). | Edu Moura | Not specified | Customer Success | Issue of blueprint documents | Delivered | On Track | We have successfully integrated WxCC into the CSM Lifecycle dashboard, including all playcards. We have booked an enablement session for June 10th to walk the Collaboration CSMs through these additions. | With our primary CoE playbook contact returning from paternity leave in June, we can move forward with exploring how to replicate the Playbook portal for the CSM team. |  |  |  | 2026-06-01 10:42 | Jun 4 (June MBR) | 1
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Marketing | Strategic Messaging & Communications | Drive post-sale adoption as a core operating motion | Drive sustained Webex Contact Center adoption beyond go-live | Marcus Quinn | Marcus Quinn | Customer Success | (Duplicate measure) Number of Opportunities raised by CSM team | 100 WxCC/AI Opportunities raised | On Track | Q4 Total = 2 | Slow start to the Qtr - pushing the team to focus for next 2 months |  |  |  | 2026-06-09 09:34 | Jun 4 (June MBR) | 1
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Marketing | Strategic Messaging & Communications | Drive post-sale adoption as a core operating motion | Reduce zero-usage Cloud Contact Center customers | Kamesh Chidambaram | Kamesh Chidambaram | Customer Success | Reduction of zero-usage Cloud customers from Q4FY25 of 9%/125 customers | 25% reduction | On Track | 86 Tenants | No usage tenants count stands at 86 tenants (6%), compared to 106 tenants (7%) at end Q3​ |  |  |  | 2026-06-09 09:32 | Jun 4 (June MBR) | 1
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Marketing | Strategic Messaging & Communications | Improve CX renewal rates and contract duration | Execute renewals for existing contact center customers | Edu Moura | Edu Moura | Customer Success | WxCC Renewal Rate | 90% Renewal rate - WxCC | On Track | ​Q4 WxCC renewal is currently at 48.0% | ​Q4 WxCC renewal is currently at 48.0%, with 3,740 of 7,785 scoped seats renewed. The largest opportunity is the remaining renewal base: 2,871 seats across 101 accounts, representing $2.66M AOV still up for renewal. |  |  |  | 2026-06-03 02:08 | Jun 4 (June MBR) | 1
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Marketing | Strategic Messaging & Communications | Maintain product quality and availability | Maintain product quality and availability [CPaaS] | Rama Krishna Balapalle | Tim Strike | CPaaS | Tracks the average availability percentage across CPaaS sites. | 99.95% | On Track | 100% | May 100% platform availability, with two channel-impacting incidents with RCS delivery in US AWS and Azure environments |  |  |  | 2026-06-02 00:34 | Jun 4 (June MBR) | 1
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Marketing | Strategic Messaging & Communications | Maintain product quality and availability | Maintain product quality and availability [WxCC] | Ravi Kiran Vadlamani | Marie Prentice | Engineering | Tracks the percentage of time WxCC meets established quality standards and is available to customers. | 99.99% | On Track | 99.995%​ | Availability was impacted by two P1 incidents that affected US Prod1. |  |  |  | 2026-06-09 16:55 | Jun 4 (June MBR) | 1
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Marketing | Strategic Messaging & Communications | Maintain product quality and availability | Maintain product quality and availability [WxCCE] | Krish Padmanabhan | Suresh Hariharan | Engineering | Tracks the percentage of time WxCCE meets established quality standards and is available to customers. | 99.995% | Off Track/Delayed | May 2026 Platform Availability - 99.819% May 2026 Overall Availability - 99.986% | Platform availability impact due to DC outages (Almere and Denver) Platform availability has impacted a subset of customers (Geo based) and hence the variance Customer Escalations: 33 (SLA-5) (Cisco:14/ Part/Cust: 19) SLA impacting customers - Propharma(Wx011), Tesco(Wx019), Capgemini(Wx020), Portland General Electric(Wx043), Kaiser Permanente NCS(Wx054) |  |  |  | 2026-06-10 06:11 | Jun 4 (June MBR) | 2
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Marketing | Strategic Messaging & Communications | Maintain product quality and availability | Maintain product quality for on-prem customers | Krish Padmanabhan | Suresh Hariharan | Engineering | Monitors the number of OnPrem customer sites requiring critical escalation or urgent issue resolution, targeting zero CAP and Hot sites. | 0 CAP sites 0 Hot sites | On Track | No active CAP or Hotsite | Verizon issue was handled well and appreciated by Customer and Accounts team |  |  |  | 2026-06-10 06:15 | Jun 4 (June MBR) | 2
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Marketing | Strategic Messaging & Communications | Reduce operational friction through in-life automation | Deliver automation for repeatable FAQ use cases | Martin King | Not specified | Help Desk & Solution Management | CSM Portal AI Agent resolving cases by use of knowledge base | 30% resolved by AI Agent | On Track | Knowledge Base Rate 51% | Increased as a result of more than 50% of Envoy ticket flow.​ |  |  |  | 2026-06-04 10:34 | Jun 4 (June MBR) | 1
4 | Accelerate AI Growth and Adoption | Product Management | On Prem Product Management | Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | Deliver in-life management telemetry for AI | Manali Dongre | Manali Dongre | Cloud Product Management | Number of features delivered | 3 features/capabilities | At Risk | 1.5 features done | - AI Assistant in PowerBI - Done - Feature usage metrics - 90% of usage metrics needed by In-Life and Customer Success teams were available in Amplitude and PowerBI. There is a retention issue that is being worked on with WAP teams. - Operational metrics - 30% available in Amplitude and are made available. For remaining, approach being explored with the Data team to get the data into Splunk (since Platform team has moved Grafana metrics to Splunk and moving to Splunk is needed for TAC). Solution being explored to see whether reports need to be built in Splunk or PowerBI. Targeted for something in Q4 else will slip to Q1. However, PM driving this area was impacted and so looking to transition this to another PM |  |  |  | 2026-05-27 12:18 | Jun 4 (June MBR) | 1 | 3
4 | Accelerate AI Growth and Adoption | Product Management | On Prem Product Management | Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | Enhance reporting & analytics for AI products including ROI | Manali Dongre | Manali Dongre | Cloud Product Management | Number of features delivered | 5 features/capabilities. Excluding observability. | Off Track/Delayed | 0 features | Reporting for AI QM - Human Agent reports in Analyzer will be in June. For AI Agents planned for July beta. Reporting for AI Assistant - Delayed to Q1/Q2FY27 due to prioritizing AI Assistant Get Well Plan. Reporting for AI WFM - In Planning. Planned for Q1FY27 Analyzer feature - Comprehensive Home page on track for July GA. Analyzer feature - Streamlined create visualization - August/Sept beta. GA will be delayed to Q1FY27. |  |  |  | 2026-05-27 12:16 | Jun 4 (June MBR) | 1 | 5
4 | Accelerate AI Growth and Adoption | Product Management | On Prem Product Management | Enable the field and partners to confidently sell AI | AI Cookbooks | Chandramouli Vaithiyanathan | Maurice Lopes | AI Solution Consulting Group | Create reference and repeatable playbooks that can be used in every AI SCG deployment to show what good looks like | Published AI Agent cookbook and used in 100% of all AI Agents developed by SCG and integrations available in the MCP factory. | On Track |  | CookBook will be made public on Jun 5th |  |  |  | 2026-06-02 20:33 | Jun 4 (June MBR) | 1
4 | Accelerate AI Growth and Adoption | Product Management | On Prem Product Management | Make AI easy to start and hard to abandon | Dog and Pony Show | Dan Mathews | Not specified | AI Solution Consulting Group |  | N/A | At Risk | Met with the account teams for all target GES opportunities and segmented them based on relationship and investment. SCG and COW are engaged in the investment accounts, but executive / GTM involvement is required in the majority of GES accounts to rebuild the relationship and capture mindshare. |  |  |  |  | 2026-05-31 18:44 | Jun 4 (June MBR) | 1
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Context driven orchestration | Deliver new data capabilities including AI memory, context graph and JDS onboarding​ | Manali Dongre | Manali Dongre | Cloud Product Management | Number of features/capabilities/services enabled | 4 features | At Risk | 0 features | AI Memory: Cisco Live Demo on track. Early Access planned in July. GA in Q1FY27. Identity Management: Delayed to Q2FY27. Queue entity (2 features) - Need to remove from this method |  |  |  | 2026-05-27 12:13 | Jun 4 (June MBR) | 1 | 4
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Context driven orchestration | Deliver real time AI insights capabilities (e.g., create AI agent, etc.) ​ | Manali Dongre | Manali Dongre | Cloud Product Management | Number of features/capabilities enabled | 3 features | Not specified |  | Anomaly detection: At Cisco Live, WFM insights are being prioritized. Beta to come in August with GA in Q1FY2027. Topics -> Automation workflow: Team is heads down with multi-lingual and will work on this in parallel. Beta in July is hopeful. GA in Q1FY2027 However, if we decide to prioritize include Topics in the default license then the above will be impacted. |  |  |  | 2026-05-27 12:14 | Jun 4 (June MBR) | 1 | 3
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Context driven orchestration | Launch AI routing capabilities | Brian Heikes | Brian Heikes | Cloud Product Management | Customers using AI routing | 5 beta customers using AI Routing & 3 features delivered including 1 beta | On Track | Beta live, seeking additional customers. |  |  |  |  | 2026-06-09 14:13 | Jun 4 (June MBR) | 1 | 3
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Context driven orchestration | Turn active data into signals that power an insights-to-action architecture | Manali Dongre | Manali Dongre | Cloud Product Management | Number of features/capabilities/services enabled | 3 features | Off Track/Delayed | 0 features | Topic Analytics to apply to Digital and AI Agent interactions: Delayed to Q1FY27 due to dependency on transcripts for digital and AI Agent interactions aligning to a common format. Insights Orchestration: Demo for Cisco Live focused on WFM. Planned Beta for Q1FY27. |  |  |  | 2026-05-27 12:12 | Jun 4 (June MBR) | 1 | 3
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Extensible AI native platform | Address critical adminstrative experience gaps to address Gartner feedback (e.g., TMP, asset mgmt from connect, simplify setup, etc.)​ | Brian Heikes | Brian Heikes | Cloud Product Management | Number of features delivered | 5 features released | At Risk | 4 GA in H2 | Remaining FIRA of 6143 'Connect/Engage integration with CC and CCE' at risk due to dependencies. Teams working through planning to re-confirm dates and blockers. |  |  |  | 2026-05-27 16:51 | Jun 4 (June MBR) | 1 | 4
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Extensible AI native platform | Close critical billing gaps (data pipeline, CPaaS)​ | Brian Heikes | Brian Heikes | Cloud Product Management | Number of features delivered | 5 features/epics delivered | At Risk | 2 features delivered | LR impacts on Billing PM putting significant pressure on team to maintain momentum. Lack of Rev Assurance for CC means PM is spending significant time filling gaps with fewer people. |  |  |  | 2026-06-09 21:43 | Jun 4 (June MBR) | 1 | 8
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Extensible AI native platform | Close remaining STC features | Manali Dongre | Betty Mai | Cloud Product Management | Remaining 4 features of STC initiative. | 4 features | On Track | 2 features are GA (2374 and 5023) Remaining 2 features in Early Access (1272, 6128) with GA in June. | 2 features are GA (2374 and 5023) Remaining 2 features in Early Access (1272, 6128) with GA in June. |  |  |  | 2026-05-27 11:08 | Jun 4 (June MBR) | 1 | 4
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Extensible AI native platform | Deliver approved market access initiatives - India | Kirsty Newsham | Kirsty Newsham | Cloud Product Management | Number of phases delivered | Number of phases delivered | Off Track/Delayed |  | India DC phase 2 - WebRTC. Delayed due to WxC dependency. Target GA has moved from July 26 to Oct 26. Amey has advised this cannot be delivered in Q4 but the team are assessing if they can deliver this earlier in Q1. India DC Phase 3 – Multi-Tenancy. At risk. Currently ranked as Priority 2.8; awaiting formal grooming to finalize technical requirements. Due to volume of work for admin this is at risk. We are currently reviewing trade-offs necessary to accelerate. |  |  |  | 2026-05-26 17:53 | Jun 4 (June MBR) | 1 | 1
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Extensible AI native platform | Deliver native AI WEM (e.g., forecasting/scheduling maturity, reporting, intraday, call recording, etc.)​ | Sivacharan Bandi | Manali Dongre | Cloud Product Management | Number of workloads available in EA | 6 Workloads (MVO in Beta) - WFM; AI QM; Performance Management; AI Powered Assistant; Onboarding; Voice of the Employee | At Risk | 2 workloads GA (AI QM and AI Assistant) 1 workload in Beta (WFM) 2 workloads inprogress (AI Training, Performance Managemen) | Recording Management -Recording Management in Control Hub GA'd. Updated priorities based on field feedback on compliance recording. Will be working with engineering on those next. AI QM and AI Assistant workloads are GA. AI Agent GA WFM - Forecasting is in Beta (Estes is enabled). Scheduling has a few issues and can be demo'd with beta in Q4. Intraday Beta in July with GA for all in Q1 Performance Management - Agent Central first version will Beta in June with GA in August. AI training - Cisco Live Demo with Beta in Q1. GA will be Q2. Voice of Employee - Q1/Q2 Beta - Deferred until we get through some other workloads. |  |  |  | 2026-05-27 10:09 | Jun 4 (June MBR) | 1 | 15
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Extensible AI native platform | Enhance vertical focus on healthcare: EPIC integrations | Brian Heikes | Brian Heikes | Cloud Product Management | Number of microservices with Epic enabled | 4 features | On Track | 1 Q4 feature GA | Pause/Resume recording support GA'd on May14, outbound dialer on track for late June. |  |  |  | 2026-05-27 16:48 | Jun 4 (June MBR) | 1 | 4
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Extensible AI native platform | Extend integrations with key ecosystem partners (Salesforce/Service Now) | Brian Heikes | Brian Heikes | Cloud Product Management | Number of features/connectors (Salesforce + Service Now) delivered | 3 features | On Track | 1 (SCV live) | SCV live after offer/billing delay. Ongoing discussions on if BYOCCaaS Plan should be modified based on desire to keep routing on our platform - which would mean skipping planned BYO Phase 1. |  |  |  | 2026-05-27 17:06 | Jun 4 (June MBR) | 1 | 3
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Extensible AI native platform | Initiate foundational efforts to support FedRAMP | Kirsty Newsham | Kirsty Newsham | Cloud Product Management | FedRAMP for WxCC | Gap assessment completed and development started | On Track | In discovery | Business case & MAF fully approved on 5/5. still in the discovery phase and working on architecture diagram. delays to red badge onboarding for compliance gap assessment due to procurement issue (waiting an update on this from Debbie Biddwell) |  |  |  | 2026-06-11 16:55 | Jun 4 (June MBR) | 1 | 1
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Extensible AI native platform | Multi-Region Disaster Recovery for Webex Contact Center | Brian Heikes | Not specified | Cloud Product Management |  |  | Planning | Planning | Planning underway, but may need prioritization calls on if we have to make tradeoffs to hit timeline. |  |  |  | 2026-05-27 16:55 | Jun 4 (June MBR) | 1 | 1
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Intelligent front door | Accelerate digital channel enablement (including functionality/ flow/ onboarding/ expansion)​ | Manali Dongre | Manali Dongre | Cloud Product Management | Number of features delivered | 8 features | At Risk | 0 done | Out of 8 features - 7 in Development (3 in June, 1 in July, 3 GA in Sept). 1 in Planning Sept GA - Pause and Resume, Digital Data gaps, Channel type aggregation - large changes with significant data dependencies. Flow consolidation has multiple jiras. Not all are tracked here. This will flow into Q1 for GA. |  |  |  | 2026-05-27 11:15 | Jun 4 (June MBR) | 1 | 8
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Intelligent front door | Continue to drive best in class AI Agent voice experience | Manoj Muthavarapu | Manoj Muthavarapu | Cloud Product Management | Number of features | - 4 features - 1 S2S engine (beta/EA) - Voicea for scripted; autonomous stretch | At Risk | WxCC-11519 (S2S engine with AWS Novasonic) - Green WxCC-4562 (Soniox based AI engine for Concierge) - Amber WxCC-10394 (Voicea ASR for scripted agents) - Deprioritized | WxCC-11519 (S2S engine with AWS Novasonic) Further fixes based on early feedback done. This is in a good shape for CLUS demos but doesn't yet support multi-agent orchestration - that is the next milestone being targeted. WxCC-4562 (Soniox based AI engine for Concierge) - stretch feature Ready as a concierge engine but with the older 4.1-mini model. Early feedback showed that the conversational experience is good but the LLM responses are poor and flat (given the mini model). We were using this mainly to leverage PTUs but will now need to consider moving to 5.1-mini or abondon pursuing a pipeline based model for concierge and just stick to S2S models for concierge. Changing overall status to "At risk" to capture the GPS issue with Soniox and the contingency planning needed |  |  |  | 2026-05-27 14:00 | Jun 4 (June MBR) | 1 | 7
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Intelligent front door | Deliver enhancements to AI Agent Studio (e.g., Developer enablement, testing, AI engine, observability, security, knowledge, and CX desktop) | Manoj Muthavarapu | Manoj Muthavarapu | Cloud Product Management | Number of features | 20 features delivered including - Observability - MVO with 3 features - AI engines - BYO-AI with 2 feature - Dev XP - 8 features - Knowledge - 3 features (additional connector and enhancements) - Security - 4 features | Off Track/Delayed | Observability & Analytics - 3 on track, 1 slightly late and 1 delayed. AI engines - 1 deferred, 2 completed, 1 delayed Studio & dev experience - 1 completed, 1 on track, 2 late Knowledge - 2 late, 1 deprioritized, 1 added Security - 1 on track, 2 late | Observability 1\. WxCC-10723 (Observability metrics for Phase 1) - slightly late. Work is set to start from the coming sprint, but RBAC/date closure is still pending before this fully moves into DEV. 2\. WxCC-11721 (Observability dashboards) - on track. The dashboard shape is still moving forward, with RBAC and scope decisions being closed alongside the metrics work. 3\. WxCC-7711 (Simulated testing) - under active development. Team is keeping this on its current GA track and pushing net-new architecture work outside this FIRA. 4\. WxCC-6288 (Analyzer integration) - slightly late. GT is still being worked through and there are open data discrepancy issues to clear. 5\. WxCC-6232 (Transcript standardization / storage) - quite delayed. Service/version issues are still being worked through and the latest note was to avoid demoing this until after Cisco Live. AI engines 1\. WxCC-6290 (BYO AI engine) - deferred to Q1. 2\. WxCC-11669 (Pro-Europe engine) - completed / GA. 3\. WxCC-9986 (MCP support) - completed / GA. 4\. WxCC-9987 (Multi-agent orchestration with A2A) - delayed. mainly due to the prioritization of AI receptionist and AI assistant work items Studio & developer experience 1\. WxCC-6189 (AI optimized prompts) - on track. development continues. 2\. WxCC-8727 (Transfer actions) - running late. GA targeted for May 30 but multiple bugs discovered that need to be fixed. Feature is available to be turned on for select orgs as needed. 3\. WxCC-6525 (Custom event support) - completed / GA. 4\. WxCC-12767 (Sync timezone with org config) - delayed. should have been done in Q3 but has slipped into Q4 Knowledge 1\. WxCC-10649 (Knowledge aggregator integration) - deprioritized in favor of sharepoint connector 2\. WxCC-12314 (Many-to-many KB mapping / file download path) - slightly late. Still in capture and waiting for backend prioritization once higher-priority asks clear. 3\. WxCC-11936 (RAG ingestion improvements) - delayed but will be completed soon. Security 1\. WxCC-12925 (Guardrail controls) - cancelled. The original Jira is cancelled and this is now being folded into the broader AI Defense FIRA 2\. WxCC-11788 (AI defense - custom guardrails) - slightly late but ready for CLUS demos 3\. WxCC-13843 (Multi-turn guardrail) - delayed. Progress is blocked as the devs are busy supporting ai assistant get well plan 4\. WxCC-13953 (AI defense - extended guardrails) - delayed. likely to spill over into Q1 |  |  |  | 2026-05-27 14:01 | Jun 4 (June MBR) | 1 | 25
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Intelligent front door | Task Agent Orchestration Framework | Manoj Muthavarapu | Manoj Muthavarapu | Cloud Product Management | Create multi-agent orchestration framework and launch a preview; Deliver features. | Create multi-agent orchestration framework and launch a preview. Deliver 2 features in FY26. | Off Track/Delayed | No major productization work started on this beyond A2A / transfers | Active productization on this track will begin after we deliver the concierge framework |  |  |  | 2026-05-27 14:02 | Jun 4 (June MBR) | 1 | 2
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Unlock team potential and development excellence | Accelerate SDLC changes in the age of AI including AI enablement for execution (knowledge for LLMs etc) | Ravi Kiran Vadlamani | Ravi Kiran Vadlamani | Engineering | Cut in half average feature delivery time from Capture -> GA | 50% | Complete |  | Dramatically reduced feature delivery time by over 50%. Average time spent for Discovery to Development went from 279 days to 130 days. This was primarily through cleanup and focused grooming workshops. |  |  |  | 2026-06-10 21:03 | Jun 4 (June MBR) | 1
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Unlock team potential and development excellence | CPaaS: Use AI tools to drive efficiency | Rama Krishna Balapalle | Venkata Nidadavolu | Engineering | Leverage AI tools to achieve a 50% increase in delivery capacity by the end of FY26 | 50% | On Track | 100% | WxCoonnect & Gateway teams continued to delivered 50% story points. We are seeing potential to increase this further. We will revise this in Q1FY27. |  |  |  | 2026-06-11 21:02 | Jun 4 (June MBR) | 1
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Unlock team potential and development excellence | Deliver media convergence | Ravi Kiran Vadlamani | Ravi Kiran Vadlamani | Engineering | Use a common media server for Calling, Meetings & CC | 10% | On Track | 2% | Development kicked off in both CC & Calling side. GA by FY27Q3. |  |  |  | 2026-06-10 21:02 | Jun 4 (June MBR) | 1
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Unlock team potential and development excellence | Drive upskilling of teams through training and rotations (product knowledge, use of AI, new areas, etc.) | Chang Chang | Shreya Pal | Cloud Product Management | % of PM team to take training | For PM team: 100% of PMs take training; 100% utilization of AI for requirements capture, prototyping;100% of targeted PM rotations | On Track | 60% | PM Training delivered, 100% of targeted PM rotation to new areas complete, use of AI in progress (~80% actively using AI) |  |  |  | 2026-06-11 16:36 | Jun 4 (June MBR) | 1
5 | Deliver Meaningful Product Differentiation and Velocity | GTM; Customer Success; Solutioning | GTM | Unlock team potential and development excellence | Use AI tools to drive efficiency (WxCC, CCE) | Ravi Kiran Vadlamani | Betty Mai | Engineering | Use AI to support developer code creation and look to generate 50% of code PRs with GenAI by end FY26 | 50% of code PRs | On Track | 86% | 86% of code pull requests used GenAI in Q3. Teams continue to integrate AI into development processes. |  |  |  | 2026-06-10 21:25 | Jun 4 (June MBR) | 1
6 | Strengthen Market Positioning and Routes to Market | GTM; Customer Success; Solutioning | GTM | Establish new and expand existing strategic technology partnerships | Establish process and governance for technology partnership decisions and approvals | Tom Clifford | Not specified | Collab GTM | Agreed upon slide deck summarizing new partner evaluation process; role of various stakeholders; timelines; and decisions taken to onboard new partners. | Streamline End to End Onboarding time / duration; from partner initial identification to SKU activation, reducing effort and increasing capacity of the team | On Track | On track | Taking slightly longer to implement than expected but no particular blockers, should be complete by end of June |  |  |  | 2026-06-08 08:01 | Jun 4 (June MBR) | 1
6 | Strengthen Market Positioning and Routes to Market | GTM; Customer Success; Solutioning | GTM | Establish new and expand existing strategic technology partnerships | Expand and agree new GTM technology partnerships | Tom Clifford | Not specified | Collab GTM | Strategic partnerships identified and/or announced | - SF SCV/BYO CCaaS - SNOW Integration | On Track | On Track | Taking slightly longer to implement than expected but no particular blockers, should be complete by end of June |  |  |  | 2026-06-08 08:01 | Jun 4 (June MBR) | 1
7 | Other | GTM; Customer Success; Solutioning | GTM | Address billing issues and reduce unbilled revenue | Reduce Unbilled revenue | Jacq Hattingh | Jacq Hattingh | Customer Success | Have no customers with unbilled revenue for 3 consective months. | Have no customers with unbilled revenue for 3 consective months | On Track | April total = $2.59M Resolved = $1.15M New May = $1.89M May Total = $3.33M | Backlog improved but new May drove the increase |  |  |  | 2026-06-08 08:05 | Jun 4 (June MBR) | 1
7 | Other | GTM; Customer Success; Solutioning | GTM | Retain CPaaS run rate business | Shutdown legacy CPaaS platforms | Nir Feldberg | Not specified | CPaaS | Reduce # of CPaaS Legacy platforms. | Shut down X, Y | On Track | Smarthub - Notify Shared environment customers have migrated Textlocal - Textlocal is now End of Sale, no more credits can be purchased, which should help the push to migrate final customers | Smart Hub - By end of July Q4 60% SH traffic will have migrated, 100% by end of Q1 Textlocal - Barclays to Campaign in progress and on track. Follow up comms to remaining customers in progress for final push to Interact. Preparation for decommissioning tasks is underway |  |  |  | 2026-06-04 10:38 | Jun 4 (June MBR) | 1
| Not linked in Airtable |  |  | Not linked | Deliver impactful OneCisco experiences: CCaaS + UCaaS (reporting) | Manali Dongre | Manali Dongre | Cloud Product Management | Number of impactful use cases delivered | 1 feature launch | On Track |  | currently in EA, and expected to go GA by EOM/early july |  |  |  | 2026-06-11 17:01 | Jun 4 (June MBR) | 1 | 1

## TL Dated Updates
H2 Order | H2 Value | Top-Level Method | Update Date | Reporting Month | Reporting Period | Status | Actual | Commentary | Obstacles
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | Execute disciplined migration from on-prem to Webex Contact Center | 2026-06-03 12:05 | Month 2 | Jun 4 (June MBR) | At Risk | 3.7% (1.0K / 27K) | Migration to the cloud is behind plan due to restrictive CCX offer criteria (75% of deals fail to qualify for the migration tool) and a lack of CCE-to-WxCC migration tool or incentives. The Collaboration GTM is currently revamping commercial offers to improve the value proposition and accelerate cloud adoption.
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | Protect and grow renewal revenue in the installed base | 2026-05-12 10:24 | Month 2 | Jun 4 (June MBR) | On Track | 5/12 - 75% (102k of 137k ATR) have renewed, with 5% (5.6k of 102k) migrating to cloud. YTD, 73% of FY26 ATR has renewed, with 4% migrating to cloud. | 5/12 - caught up and exceeding the q4 renewal target of 73%, still striving to achieve the H2 Bridge plan stretch target of 79% renewing. The cloud migration target is still unlikely to be achieved though.
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | Protect and grow renewal revenue in the installed base | 2026-06-03 12:08 | Month 2 | Jun 4 (June MBR) | At Risk | 54% renewed from Q4M1 ATR (14.8k from 27.4k) 902.7k seats | 42% of Q4 ATR renewed, 13% lost, 6% downsell, 42% still available to be renewed.
2 | Win Greenfield, Enterprise Contact Center Customers | Deliver product features specifically blocking large, impactful enterprise deals | 2026-06-11 16:44 | Month 2 | Jun 4 (June MBR) | On Track | 2 in progress | See commentary below | Clarity on list of features prioritized from COE with impact
2 | Win Greenfield, Enterprise Contact Center Customers | Expand enterprise demand through adjacency and One Cisco motions | 2026-05-12 11:04 | Month 2 | Jun 4 (June MBR) | On Track | 5/12 - FY27 plan should be finalised followng this weeks meetings in NY | 5/12 - FY27 Collaboration Product GTM plan focuses on 3 pillars: 1. AI Attach 2. Grow Devices business by 100% 3. Foundational
2 | Win Greenfield, Enterprise Contact Center Customers | Unblock enterprise deals through product and pricing | 2026-05-12 10:30 | Month 2 | Jun 4 (June MBR) | Off Track/Delayed | 5/12 - 0 deals booked and only 117 greenfield seats booked QTD. YTD, there are 0 deals booked with >1000 seats and 1,447 greenfield seats booked vs target of 40k. | 5/12 - Entergy deal was lost to Genesys, Providence is still a Q4 opportunity expected to close in Q4.
2 | Win Greenfield, Enterprise Contact Center Customers | Unblock enterprise deals through product and pricing | 2026-06-03 12:12 | Month 2 | Jun 4 (June MBR) | At Risk | 2 deals >= 1k seats 1.3K greenfield seats | 2 deals, DSV & MakeMyTrip booked 10,00 seats in M9.
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Drive expansion of Webex Contact Center | 2026-06-03 02:12 | Month 2 | Jun 4 (June MBR) | At Risk | 2 WxCC opportunities | Only 2 opportunities raised so far against target of 25 in Q4. However, we exceeded target in Q3 at 35. | Lack of direct access to Agent/CC KPI telemetry means we need to get Partner+Customer approval to build and run a report to analyse. Dependency on Product to remove this obstacle
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Drive post-sale adoption as a core operating motion | 2026-06-09 09:33 | Month 2 | Jun 4 (June MBR) | On Track | 86 Accounts | No usage tenants count stands at 86 tenants (6%), compared to 106 tenants (7%) at end Q3​
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Improve CX renewal rates and contract duration | 2026-06-03 02:10 | Month 2 | Jun 4 (June MBR) | On Track | ​Q4 WxCC renewal is currently at 48.0% | ​Q4 WxCC renewal is currently at 48.0%, with 3,740 of 7,785 scoped seats renewed. The largest opportunity is the remaining renewal base: 2,871 seats across 101 accounts, representing $2.66M AOV still up for renewal.
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Maintain product quality and availability | 2026-06-09 20:26 | Month 2 | Jun 4 (June MBR) | At Risk | WxCCE: May SLA uptime - 99.995%, Platform - 100%, 0 CAP / 0 Hot WxCC: May Global 99.995% CPaaS: May 100% Platform Availability | Availability in May showed strong performance across the portfolio. WxCCE achieved a May SLA uptime of 99.995% with platform availability at 100%, reporting no CAP or Hot Site issues. A Verizon-related incident was managed effectively and received positive feedback from both the Customer and Accounts teams. WxCC recorded a global availability of 99.995%, though impacted by two P1 incidents affecting the US Prod1 environment. CPaaS maintained 100% platform availability despite experiencing two channel-impacting incidents related to RCS delivery in the US AWS and Azure environments.
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Maintain product quality and availability | 2026-06-10 15:43 | Month 2 | Jun 4 (June MBR) | On Track | WxCCE: May Platform Availability - 99.819%, May 2026 Overall Availability - 99.986%, 0 CAP / 0 Hot WxCC: May Global 99.995% CPaaS: May 100% Platform Availability | Availability for WxCCE in May 2026 showed platform availability at 99.819% and overall availability at 99.986%, impacted by data center outages in Almere and Denver affecting some customers geographically. There were 33 customer escalations, with five customers experiencing SLA-impacting issues: Propharma, Tesco, Capgemini, Portland General Electric, and Kaiser Permanente NCS. WxCC recorded a global availability of 99.995%, though impacted by two P1 incidents affecting the US Prod1 environment. CPaaS maintained 100% platform availability despite experiencing two channel-impacting incidents related to RCS delivery in the US AWS and Azure environments.
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Maintain product quality and availability | 2026-06-10 15:46 | Month 2 | Jun 4 (June MBR) | At Risk | WxCCE: May Platform Availability - 99.819%, May 2026 Overall Availability - 99.986%, 0 CAP / 0 Hot WxCC: May Global 99.995% CPaaS: May 100% Platform Availability | Availability for WxCCE in May 2026 showed platform availability at 99.819% and overall availability at 99.986%, impacted by data center outages in Almere and Denver affecting some customers geographically. There were 33 customer escalations, with five customers experiencing SLA-impacting issues: Propharma, Tesco, Capgemini, Portland General Electric, and Kaiser Permanente NCS. WxCC recorded a global availability of 99.995%, though impacted by two P1 incidents affecting the US Prod1 environment. CPaaS maintained 100% platform availability despite experiencing two channel-impacting incidents related to RCS delivery in the US AWS and Azure environments.
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Reduce operational friction through in-life automation | 2026-06-04 10:31 | Month 2 | Jun 4 (June MBR) | At Risk | 72.4% | Need for Human support rate increased due to high failure rates on Webex Campaign and Notify
4 | Accelerate AI Growth and Adoption | Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | 2026-06-11 16:16 | Month 2 | Jun 4 (June MBR) | Off Track/Delayed | 1.5 | Reporting for AI QM - Human Agent reports in Analyzer will be in June. For AI Agents planned for July beta. Reporting for AI Assistant - Delayed to Q1/Q2FY27 due to prioritizing AI Assistant Get Well Plan. Reporting for AI WFM - In Planning. Planned for Q1FY27 Analyzer feature - Comprehensive Home page on track for July GA. Analyzer feature - Streamlined create visualization - August/Sept beta. GA will be delayed to Q1FY27. AI Assistant delivered in PowerBI | "Clarity on requirements from field (SCG, COE, in-life teams)"
4 | Accelerate AI Growth and Adoption | Enable the field and partners to confidently sell AI | 2026-06-11 11:13 | Month 2 | Jun 4 (June MBR) | On Track | 78 usecases published to the usecase library. | 78 usecases published to the usecase library. Many of these are in the pipeline to become externally referencable.
4 | Accelerate AI Growth and Adoption | Make AI easy to start and hard to abandon | 2026-06-03 12:14 | Month 2 | Jun 4 (June MBR) | Off Track/Delayed | **WxCC Installed base:** \- AI Agent: 10% \- AI Assistant: 10% \- Overall Attach: 13% **New orders:** \- AI Agent: 20% \- AI Assistant: 13% \- Overall Attach: 24% | Cisco attach and adoption challenges are primarily due to Offer Setup, Positioning and Coverage challenges. Next steps: GTM plan for better AI positioning and coverage. Product plan to support with pre-built use cases and vertical focus.
4 | Accelerate AI Growth and Adoption | Make AI easy to start and hard to abandon | 2026-06-11 11:15 | Month 2 | Jun 4 (June MBR) | At Risk | WxCC Installed base: \- AI Agent: 10% \- AI Assistant: 10% \- Overall Attach: 13% New orders: \- AI Agent: 20% \- AI Assistant: 13% \- Overall Attach: 24% | For Q4, we are manually reaching out to the RMs to drive attach - atleast uncommitted so that the activation is done. By end of Q4, we will report on uncommitted attach as well because that is an important metric - they are not being reflected today.
5 | Deliver Meaningful Product Differentiation and Velocity | Context driven orchestration | 2026-06-11 16:32 | Month 2 | Jun 4 (June MBR) | Off Track/Delayed | 0 | See specific comments below | Completion of capture/requirements gathering. Defining the 'what'
5 | Deliver Meaningful Product Differentiation and Velocity | Extensible AI native platform | 2026-06-11 16:21 | Month 2 | Jun 4 (June MBR) | Off Track/Delayed | 12 | See specific commentary below | "Clarity on list of features prioritized from field ((SCG, COE, in-life teams) with impact", Fragmented triad in key areas such as admin
5 | Deliver Meaningful Product Differentiation and Velocity | Intelligent front door | 2026-06-11 16:23 | Month 2 | Jun 4 (June MBR) | Off Track/Delayed | 0 | See specific commentary below | "Clarity on list of features prioritized from field ((SCG, COE, in-life teams) with impact"
5 | Deliver Meaningful Product Differentiation and Velocity | Trusted & Secure by design | 2026-06-11 17:24 | Month 2 | Jun 4 (June MBR) | At Risk | 2 in progress | AI Defense update captured in AI Studio update, other features on track | Clarity on problem statements and business cases, "Reciprocating support, product prioritization & GTM alignment", Commercial offer
5 | Deliver Meaningful Product Differentiation and Velocity | Unlock team potential and development excellence | 2026-06-11 22:26 | Month 2 | Jun 4 (June MBR) | On Track | See below for current actuals | Engineering initiatives are showing strong progress, with the SDLC acceleration effort successfully meeting its goal of cutting feature delivery time by over 50% (from 279 to 130 days). AI integration is driving significant efficiency, evidenced by 86% of WxCC/CCE code PRs utilizing GenAI and CPaaS teams achieving a 50% increase in delivery capacity. Simultaneously, media convergence development has officially kicked off, remaining on track for a target GA in FY27Q3.
6 | Strengthen Market Positioning and Routes to Market | Establish new and expand existing strategic technology partnerships | 2026-06-08 08:00 | Month 2 | Jun 4 (June MBR) | On Track | On Track | Taking slightly longer to implement than expected but no particular blockers, should be complete by end of June
7 | Other | Address billing issues and reduce unbilled revenue | 2026-06-08 08:11 | Month 2 | Jun 4 (June MBR) | On Track | April total = $2.59M Resolved = $1.15M New May = $1.89M May Total = $3.33M | Backlog improved but new may drove the increase
7 | Other | Grow the Cloud Contact Center business | 2026-06-03 12:16 | Month 2 | Jun 4 (June MBR) | Off Track/Delayed | Q4M1 Close - 185k seats
7 | Other | Retain CPaaS run rate business | 2026-06-09 10:49 | Month 2 | Jun 4 (June MBR) | On Track | •108% revenue growth existing customers •100% retention >$100k customers | On track to exceed the 105% revenue growth target

## SM Dated Updates
H2 Order | H2 Value | Top-Level Method | Sub-Method | Update Date | Reporting Month | Reporting Period | Status | Actual | Commentary | Obstacles
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | Execute disciplined migration from on-prem to Webex Contact Center | Migrate CCE customers to Webex Contact Center using defined offers and tooling | 2026-06-09 15:54 | Month 2 | Jun 4 (June MBR) | Off Track/Delayed | 1410 | Our cloud migration for renewed seats is currently tracking behind schedule. This is primarily driven by the lack of a CCE to WxCC migration tool and associated incentives. To address this challenge and accelerate cloud adoption, the Collaboration GTM team is evaluating our existing commercial offers and revamping our incentives to create a more compelling value proposition for our customers. Additionally, our vendor, Univnoix, is currently assessing the effort required to build a dedicated migration tool for CCE to WxCC.
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | Execute disciplined migration from on-prem to Webex Contact Center | Migrate CCX customers to Webex Contact Center through partner-led motions | 2026-06-09 15:49 | Month 2 | Jun 4 (June MBR) | Off Track/Delayed | 758 | City of Boston is first customer to go live with migration tool. The current migration offer is not achieving the intended outcomes. Until the GTM strategy and offer are updated, we anticipate continued challenges in driving improved results.
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | Modernize the on-prem base through AI innovation | AI Assistant features | 2026-06-10 13:13 | Month 2 | Jun 4 (June MBR) | At Risk | Beta in progress. | GA in Q4 at risk due to lack of support from billing and offers team
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | Modernize the on-prem base through AI innovation | Customer trials of AI Assistant features | 2026-06-10 13:15 | Month 2 | Jun 4 (June MBR) | On Track | Beta in progress | Beta customers: Nat Grid, FNB, Autozone, Lowes, Staples, MGB, B+S
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | Modernize the on-prem base through AI innovation | Deliver CCE on-prem sovereign solutions | 2026-06-10 13:11 | Month 2 | Jun 4 (June MBR) | At Risk | Beta in progress at T Mobile and started at Bajaj Finance Limited | PM role eliminated
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | Modernize the on-prem base through AI innovation | Nutanix hypervisor support for CCE | 2026-06-10 08:56 | Month 2 | Jun 4 (June MBR) | On Track | GA on track - planned for end Q4FY26 | Beta in progress: HCSC, T-Mobile, Keck
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | Modernize the on-prem base through AI innovation | Nutanix hypervisor support for PCCE 2K | 2026-06-10 13:25 | Month 2 | Jun 4 (June MBR) | On Track | Plan for GA in Q4FY26 | Also adds support for single-node hypervisor deployment
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | Protect and grow renewal revenue in the installed base | Accelerate cloud migrations (401K) | 2026-06-09 15:41 | Month 2 | Jun 4 (June MBR) | Off Track/Delayed | 2168 | Migration to the cloud is behind plan due to restrictive CCX offer criteria (75% of deals fail to qualify for the migration tool) and a lack of CCE-to-WxCC migration tool or incentives. The Collaboration GTM is currently revamping commercial offers to improve the value proposition and accelerate cloud adoption.
1 | Retain On-Prem Contact Center Base (Migrate and Renew) | Protect and grow renewal revenue in the installed base | Incentivise and upgrade CCX base to R15.0 | 2026-06-09 15:43 | Month 2 | Jun 4 (June MBR) | Planning | N/A | We are partnering with IT and Webex Analytics to build a dedicated dashboard for on-prem R15 upgrades. This tool will utilize smart licensing data to resolve current visibility gaps and allow for clear segmentation between UCCX and UCCE.
2 | Win Greenfield, Enterprise Contact Center Customers | Deliver product features specifically blocking large, impactful enterprise deals | Deliver approved critical customer commits | 2026-06-11 16:35 | Month 2 | Jun 4 (June MBR) | On Track | 2 features | 2 features delivered (Extended Email Search History (Aviva) and ability to provision contact center through wholesale. with 8 items currently in development - including features like Generic Task Routing (Pacifica), Background Noise Suppression ifor WebRTC (Lee Health), In App 'Live Chat SDK' support (Health Equity), BYOC (Cisco IT) and Analyzer Unified Reporting (WxCC & WxC) (Polyexpert) | Clarity on list of features prioritized from COE with impact
2 | Win Greenfield, Enterprise Contact Center Customers | Expand enterprise demand through adjacency and One Cisco motions | Align marketing, sales, product, and partner orgs on vertical campaigns, messaging, content and targeted account lists - WxCC and AI | 2026-05-12 11:00 | Month 2 | Jun 4 (June MBR) | On Track | 5/12 - FY27 priorities being finalised this week in NY | 5/12 - H2 bridge plans in execution and FY27 priorities aligning key stakeholders in sales, partners, marketing progressing very well.
2 | Win Greenfield, Enterprise Contact Center Customers | Expand enterprise demand through adjacency and One Cisco motions | Create One Cisco enterprise CX programs (including EA-based offers) | 2026-05-12 11:02 | Month 1 | Jun 4 (June MBR) | On Track | 5/12 - tied to overall Collaboration procing strategy work that Tim H and team are driving | 5/12 - looking to build offers to fit into existing buying models that are favourable with enterprise customers, eg EA3.0
2 | Win Greenfield, Enterprise Contact Center Customers | Expand enterprise demand through adjacency and One Cisco motions | Launch sales plays for Cisco Calling customers | 2026-06-01 11:31 | Month 2 | Jun 4 (June MBR) | On Track |  | 1) kicked off activity with renewal team for opps to end FY27 >$50k AOV (approx 220 customers), any leads will be passed to CX specialists 2) finalised target list for FY28+ customers (approx 1400), kicked off work with Marketing to review list for outbound marketing activity - awaiting output & timeline | 1) Better together product story - this is better but still not strong, 2) Commercial Offer WxCC/WxC - why buy both form Cisco, 3) Confusion over Customer Calling Assist and WxCC - when pitch what and on separate platforms so upsell difficult
2 | Win Greenfield, Enterprise Contact Center Customers | Expand enterprise demand through adjacency and One Cisco motions | Leverage Cisco’s broader installed base (networking, security, collaboration) to open CX doors. | 2026-05-25 11:07 | Month 1 | Jun 4 (June MBR) | On Track | 5/12 - Continued in progress | 5/12 - This is ongoing throughout the year - John Kiang and team continue to help identify which customers by SL1, SL2, SL3 ahave recently bought large networking, security, collaboration deals that may help sales engage and upsell CX.
2 | Win Greenfield, Enterprise Contact Center Customers | Unblock enterprise deals through product and pricing | Competitive takeout campaigns (e.g. Avaya, Genesys) | 2026-05-12 10:46 | Month 2 | Jun 4 (June MBR) | On Track | 5/12 - Genesys Top 50 progressing. | 5/12 - Team cleaning data (CAV BU name vs SAV name) so that SFDC and Gong tracking can be done. GTM team cooordinating with SDR, as they have already been collaborating with an external agency to reach out to specific accounts. There was an ask to support a light touch approach on Five9s GES and large commercial customers but recent earnings were more positive than expected, so this is being de prioritised in Q4.
2 | Win Greenfield, Enterprise Contact Center Customers | Unblock enterprise deals through product and pricing | Deliver offers from product features that unblock enterprise deals | 2026-05-12 10:49 | Month 2 | Jun 4 (June MBR) | On Track | 5/12 - Product and GTM teams aligned, relevant offer go live plans in progress | 5/12 - No Q4 deal is blocked due to delayed offer availability
2 | Win Greenfield, Enterprise Contact Center Customers | Unblock enterprise deals through product and pricing | Develop strategic portfolio pricing aligned to enterprise buying models | 2026-05-12 10:51 | Month 2 | Jun 4 (June MBR) | On Track | 5/12 - Tim Hoolihan successfully pivoting the teams to leverage customer preferred buying models | 5/12 - Offer team revising pricing strategies, moving away from BU silo'd approaches, to one that leverages EA3.0 and will build new offers to fit these customer preferred buying models
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Drive post-sale adoption as a core operating motion | Define and execute structured in-life adoption motions | 2026-06-02 11:34 | Month 2 | Jun 4 (June MBR) | At Risk | No change in customer coverage - 74% of all tech touch customers. New customer track yet to start. | Second email campaign delayed due to impacts to Marketing team. New date TBD. | Dependency on Marketing to run campaign batches
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Drive post-sale adoption as a core operating motion | Document and replicate successful expansion blueprints (white glove, events, executive engagement). | 2026-06-01 10:42 | Month 2 | Jun 4 (June MBR) | On Track | We have successfully integrated WxCC into the CSM Lifecycle dashboard, including all playcards. We have booked an enablement session for June 10th to walk the Collaboration CSMs through these additions. | With our primary CoE playbook contact returning from paternity leave in June, we can move forward with exploring how to replicate the Playbook portal for the CSM team. | Our primary point of contact for the CoE playbook is currently on paternity leave until June. This has created a temporary bottleneck in our ability to fully explore the CoE asset portal. We are currently identifying and engaging alternative stakeholders to provide the necessary support and ensure continuity in our playbook development and replication efforts during this period.
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Drive post-sale adoption as a core operating motion | Drive sustained Webex Contact Center adoption beyond go-live | 2026-06-09 09:34 | Month 2 | Jun 4 (June MBR) | On Track | Q4 Total = 2 | Slow start to the Qtr - pushing the team to focus for next 2 months
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Drive post-sale adoption as a core operating motion | Reduce zero-usage Cloud Contact Center customers | 2026-06-09 09:32 | Month 2 | Jun 4 (June MBR) | On Track | 86 Tenants | No usage tenants count stands at 86 tenants (6%), compared to 106 tenants (7%) at end Q3​
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Improve CX renewal rates and contract duration | Execute renewals for existing contact center customers | 2026-06-03 02:08 | Month 2 | Jun 4 (June MBR) | On Track | ​Q4 WxCC renewal is currently at 48.0% | ​Q4 WxCC renewal is currently at 48.0%, with 3,740 of 7,785 scoped seats renewed. The largest opportunity is the remaining renewal base: 2,871 seats across 101 accounts, representing $2.66M AOV still up for renewal.
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Maintain product quality and availability | Maintain product quality and availability [CPaaS] | 2026-06-02 00:34 | Month 2 | Jun 4 (June MBR) | On Track | 100% | May 100% platform availability, with two channel-impacting incidents with RCS delivery in US AWS and Azure environments
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Maintain product quality and availability | Maintain product quality and availability [WxCC] | 2026-06-09 16:55 | Month 2 | Jun 4 (June MBR) | On Track | 99.995%​ | Availability was impacted by two P1 incidents that affected US Prod1.
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Maintain product quality and availability | Maintain product quality and availability [WxCCE] | 2026-06-02 10:30 | Month 2 | Jun 4 (June MBR) | On Track | May SLA uptime - 99.995% Platform - 100%
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Maintain product quality and availability | Maintain product quality and availability [WxCCE] | 2026-06-10 06:11 | Month 2 | Jun 4 (June MBR) | Off Track/Delayed | May 2026 Platform Availability - 99.819% May 2026 Overall Availability - 99.986% | Platform availability impact due to DC outages (Almere and Denver) Platform availability has impacted a subset of customers (Geo based) and hence the variance Customer Escalations: 33 (SLA-5) (Cisco:14/ Part/Cust: 19) SLA impacting customers - Propharma(Wx011), Tesco(Wx019), Capgemini(Wx020), Portland General Electric(Wx043), Kaiser Permanente NCS(Wx054)
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Maintain product quality and availability | Maintain product quality for on-prem customers | 2026-06-02 10:31 | Month 2 | Jun 4 (June MBR) | On Track | No active CAP or Hotsite | Verizon issue was handled well and appreciated by Customer and Accounts team
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Maintain product quality and availability | Maintain product quality for on-prem customers | 2026-06-10 06:15 | Month 2 | Jun 4 (June MBR) | On Track | No active CAP or Hotsite | Verizon issue was handled well and appreciated by Customer and Accounts team
3 | Drive Webex Contact Center Adoption and Expansion (Existing Customers) | Reduce operational friction through in-life automation | Deliver automation for repeatable FAQ use cases | 2026-06-04 10:34 | Month 2 | Jun 4 (June MBR) | On Track | Knowledge Base Rate 51% | Increased as a result of more than 50% of Envoy ticket flow.​
4 | Accelerate AI Growth and Adoption | Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | Deliver in-life management telemetry for AI | 2026-05-27 12:18 | Month 2 | Jun 4 (June MBR) | At Risk | 1.5 features done | - AI Assistant in PowerBI - Done - Feature usage metrics - 90% of usage metrics needed by In-Life and Customer Success teams were available in Amplitude and PowerBI. There is a retention issue that is being worked on with WAP teams. - Operational metrics - 30% available in Amplitude and are made available. For remaining, approach being explored with the Data team to get the data into Splunk (since Platform team has moved Grafana metrics to Splunk and moving to Splunk is needed for TAC). Solution being explored to see whether reports need to be built in Splunk or PowerBI. Targeted for something in Q4 else will slip to Q1. However, PM driving this area was impacted and so looking to transition this to another PM | "Clarity on the data requirements (e.g., What data, normalization, etc.)"
4 | Accelerate AI Growth and Adoption | Enable product capabilities to empower stakeholders and customers to drive AI adoption and maximize usage | Enhance reporting & analytics for AI products including ROI | 2026-05-27 12:16 | Month 2 | Jun 4 (June MBR) | Off Track/Delayed | 0 features | Reporting for AI QM - Human Agent reports in Analyzer will be in June. For AI Agents planned for July beta. Reporting for AI Assistant - Delayed to Q1/Q2FY27 due to prioritizing AI Assistant Get Well Plan. Reporting for AI WFM - In Planning. Planned for Q1FY27 Analyzer feature - Comprehensive Home page on track for July GA. Analyzer feature - Streamlined create visualization - August/Sept beta. GA will be delayed to Q1FY27. | Clarity on requirements
4 | Accelerate AI Growth and Adoption | Enable the field and partners to confidently sell AI | AI Cookbooks | 2026-06-02 20:33 | Month 2 | Jun 4 (June MBR) | On Track |  | CookBook will be made public on Jun 5th
4 | Accelerate AI Growth and Adoption | Make AI easy to start and hard to abandon | Dog and Pony Show | 2026-05-31 18:44 | Month 2 | Jun 4 (June MBR) | At Risk | Met with the account teams for all target GES opportunities and segmented them based on relationship and investment. SCG and COW are engaged in the investment accounts, but executive / GTM involvement is required in the majority of GES accounts to rebuild the relationship and capture mindshare.
5 | Deliver Meaningful Product Differentiation and Velocity | Context driven orchestration | Deliver new data capabilities including AI memory, context graph and JDS onboarding​ | 2026-05-27 12:13 | Month 2 | Jun 4 (June MBR) | At Risk | 0 features | AI Memory: Cisco Live Demo on track. Early Access planned in July. GA in Q1FY27. Identity Management: Delayed to Q2FY27. Queue entity (2 features) - Need to remove from this method
5 | Deliver Meaningful Product Differentiation and Velocity | Context driven orchestration | Deliver real time AI insights capabilities (e.g., create AI agent, etc.) ​ | 2026-05-27 12:14 | Month 2 | Jun 4 (June MBR) | Not specified |  | Anomaly detection: At Cisco Live, WFM insights are being prioritized. Beta to come in August with GA in Q1FY2027. Topics -> Automation workflow: Team is heads down with multi-lingual and will work on this in parallel. Beta in July is hopeful. GA in Q1FY2027 However, if we decide to prioritize include Topics in the default license then the above will be impacted. | "SME, model creation"
5 | Deliver Meaningful Product Differentiation and Velocity | Context driven orchestration | Launch AI routing capabilities | 2026-06-09 14:13 | Month 2 | Jun 4 (June MBR) | On Track | Beta live, seeking additional customers.
5 | Deliver Meaningful Product Differentiation and Velocity | Context driven orchestration | Turn active data into signals that power an insights-to-action architecture | 2026-05-27 12:12 | Month 2 | Jun 4 (June MBR) | Off Track/Delayed | 0 features | Topic Analytics to apply to Digital and AI Agent interactions: Delayed to Q1FY27 due to dependency on transcripts for digital and AI Agent interactions aligning to a common format. Insights Orchestration: Demo for Cisco Live focused on WFM. Planned Beta for Q1FY27. | Completion of capture/requirements gathering. Defining the 'what'
5 | Deliver Meaningful Product Differentiation and Velocity | Extensible AI native platform | Address critical adminstrative experience gaps to address Gartner feedback (e.g., TMP, asset mgmt from connect, simplify setup, etc.)​ | 2026-05-27 16:51 | Month 2 | Jun 4 (June MBR) | At Risk | 4 GA in H2 | Remaining FIRA of 6143 'Connect/Engage integration with CC and CCE' at risk due to dependencies. Teams working through planning to re-confirm dates and blockers. | Fragmented triad
5 | Deliver Meaningful Product Differentiation and Velocity | Extensible AI native platform | Close critical billing gaps (data pipeline, CPaaS)​ | 2026-06-09 21:43 | Month 2 | Jun 4 (June MBR) | At Risk | 2 features delivered | LR impacts on Billing PM putting significant pressure on team to maintain momentum. Lack of Rev Assurance for CC means PM is spending significant time filling gaps with fewer people. | Data from products not reliable enough to be used for billing, CCCW not fit for purpose - usage based billling, Finance billing team not providing provisional unbilled (on time if at all)
5 | Deliver Meaningful Product Differentiation and Velocity | Extensible AI native platform | Close remaining STC features | 2026-05-27 11:08 | Month 2 | Jun 4 (June MBR) | On Track | 2 features are GA (2374 and 5023) Remaining 2 features in Early Access (1272, 6128) with GA in June. | 2 features are GA (2374 and 5023) Remaining 2 features in Early Access (1272, 6128) with GA in June.
5 | Deliver Meaningful Product Differentiation and Velocity | Extensible AI native platform | Deliver approved market access initiatives - India | 2026-05-26 17:53 | Month 2 | Jun 4 (June MBR) | Off Track/Delayed |  | India DC phase 2 - WebRTC. Delayed due to WxC dependency. Target GA has moved from July 26 to Oct 26. Amey has advised this cannot be delivered in Q4 but the team are assessing if they can deliver this earlier in Q1. India DC Phase 3 – Multi-Tenancy. At risk. Currently ranked as Priority 2.8; awaiting formal grooming to finalize technical requirements. Due to volume of work for admin this is at risk. We are currently reviewing trade-offs necessary to accelerate.
5 | Deliver Meaningful Product Differentiation and Velocity | Extensible AI native platform | Deliver native AI WEM (e.g., forecasting/scheduling maturity, reporting, intraday, call recording, etc.)​ | 2026-05-27 10:09 | Month 2 | Jun 4 (June MBR) | At Risk | 2 workloads GA (AI QM and AI Assistant) 1 workload in Beta (WFM) 2 workloads inprogress (AI Training, Performance Managemen) | Recording Management -Recording Management in Control Hub GA'd. Updated priorities based on field feedback on compliance recording. Will be working with engineering on those next. AI QM and AI Assistant workloads are GA. AI Agent GA WFM - Forecasting is in Beta (Estes is enabled). Scheduling has a few issues and can be demo'd with beta in Q4. Intraday Beta in July with GA for all in Q1 Performance Management - Agent Central first version will Beta in June with GA in August. AI training - Cisco Live Demo with Beta in Q1. GA will be Q2. Voice of Employee - Q1/Q2 Beta - Deferred until we get through some other workloads. | Sales Support, WEM SME
5 | Deliver Meaningful Product Differentiation and Velocity | Extensible AI native platform | Enhance vertical focus on healthcare: EPIC integrations | 2026-05-27 16:48 | Month 2 | Jun 4 (June MBR) | On Track | 1 Q4 feature GA | Pause/Resume recording support GA'd on May14, outbound dialer on track for late June. | Reciprocating support and prioritization, Budget/Partner
5 | Deliver Meaningful Product Differentiation and Velocity | Extensible AI native platform | Extend integrations with key ecosystem partners (Salesforce/Service Now) | 2026-05-27 17:06 | Month 2 | Jun 4 (June MBR) | On Track | 1 (SCV live) | SCV live after offer/billing delay. Ongoing discussions on if BYOCCaaS Plan should be modified based on desire to keep routing on our platform - which would mean skipping planned BYO Phase 1.
5 | Deliver Meaningful Product Differentiation and Velocity | Extensible AI native platform | Initiate foundational efforts to support FedRAMP | 2026-06-11 16:55 | Month 2 | Jun 4 (June MBR) | On Track | In discovery | Business case & MAF fully approved on 5/5. still in the discovery phase and working on architecture diagram. delays to red badge onboarding for compliance gap assessment due to procurement issue (waiting an update on this from Debbie Biddwell)
5 | Deliver Meaningful Product Differentiation and Velocity | Extensible AI native platform | Multi-Region Disaster Recovery for Webex Contact Center | 2026-05-27 16:55 | Month 2 | Jun 4 (June MBR) | Planning | Planning | Planning underway, but may need prioritization calls on if we have to make tradeoffs to hit timeline.
5 | Deliver Meaningful Product Differentiation and Velocity | Intelligent front door | Accelerate digital channel enablement (including functionality/ flow/ onboarding/ expansion)​ | 2026-05-27 11:15 | Month 2 | Jun 4 (June MBR) | At Risk | 0 done | Out of 8 features - 7 in Development (3 in June, 1 in July, 3 GA in Sept). 1 in Planning Sept GA - Pause and Resume, Digital Data gaps, Channel type aggregation - large changes with significant data dependencies. Flow consolidation has multiple jiras. Not all are tracked here. This will flow into Q1 for GA. | Clarity on list of features prioritized from COE with impact
5 | Deliver Meaningful Product Differentiation and Velocity | Intelligent front door | Continue to drive best in class AI Agent voice experience | 2026-05-27 14:00 | Month 2 | Jun 4 (June MBR) | At Risk | WxCC-11519 (S2S engine with AWS Novasonic) - Green WxCC-4562 (Soniox based AI engine for Concierge) - Amber WxCC-10394 (Voicea ASR for scripted agents) - Deprioritized | WxCC-11519 (S2S engine with AWS Novasonic) Further fixes based on early feedback done. This is in a good shape for CLUS demos but doesn't yet support multi-agent orchestration - that is the next milestone being targeted. WxCC-4562 (Soniox based AI engine for Concierge) - stretch feature Ready as a concierge engine but with the older 4.1-mini model. Early feedback showed that the conversational experience is good but the LLM responses are poor and flat (given the mini model). We were using this mainly to leverage PTUs but will now need to consider moving to 5.1-mini or abondon pursuing a pipeline based model for concierge and just stick to S2S models for concierge. Changing overall status to "At risk" to capture the GPS issue with Soniox and the contingency planning needed | Prioritization from media and other dependent teams; Offers / finance intake
5 | Deliver Meaningful Product Differentiation and Velocity | Intelligent front door | Deliver enhancements to AI Agent Studio (e.g., Developer enablement, testing, AI engine, observability, security, knowledge, and CX desktop) | 2026-05-27 14:01 | Month 2 | Jun 4 (June MBR) | Off Track/Delayed | Observability & Analytics - 3 on track, 1 slightly late and 1 delayed. AI engines - 1 deferred, 2 completed, 1 delayed Studio & dev experience - 1 completed, 1 on track, 2 late Knowledge - 2 late, 1 deprioritized, 1 added Security - 1 on track, 2 late | Observability 1\. WxCC-10723 (Observability metrics for Phase 1) - slightly late. Work is set to start from the coming sprint, but RBAC/date closure is still pending before this fully moves into DEV. 2\. WxCC-11721 (Observability dashboards) - on track. The dashboard shape is still moving forward, with RBAC and scope decisions being closed alongside the metrics work. 3\. WxCC-7711 (Simulated testing) - under active development. Team is keeping this on its current GA track and pushing net-new architecture work outside this FIRA. 4\. WxCC-6288 (Analyzer integration) - slightly late. GT is still being worked through and there are open data discrepancy issues to clear. 5\. WxCC-6232 (Transcript standardization / storage) - quite delayed. Service/version issues are still being worked through and the latest note was to avoid demoing this until after Cisco Live. AI engines 1\. WxCC-6290 (BYO AI engine) - deferred to Q1. 2\. WxCC-11669 (Pro-Europe engine) - completed / GA. 3\. WxCC-9986 (MCP support) - completed / GA. 4\. WxCC-9987 (Multi-agent orchestration with A2A) - delayed. mainly due to the prioritization of AI receptionist and AI assistant work items Studio & developer experience 1\. WxCC-6189 (AI optimized prompts) - on track. development continues. 2\. WxCC-8727 (Transfer actions) - running late. GA targeted for May 30 but multiple bugs discovered that need to be fixed. Feature is available to be turned on for select orgs as needed. 3\. WxCC-6525 (Custom event support) - completed / GA. 4\. WxCC-12767 (Sync timezone with org config) - delayed. should have been done in Q3 but has slipped into Q4 Knowledge 1\. WxCC-10649 (Knowledge aggregator integration) - deprioritized in favor of sharepoint connector 2\. WxCC-12314 (Many-to-many KB mapping / file download path) - slightly late. Still in capture and waiting for backend prioritization once higher-priority asks clear. 3\. WxCC-11936 (RAG ingestion improvements) - delayed but will be completed soon. Security 1\. WxCC-12925 (Guardrail controls) - cancelled. The original Jira is cancelled and this is now being folded into the broader AI Defense FIRA 2\. WxCC-11788 (AI defense - custom guardrails) - slightly late but ready for CLUS demos 3\. WxCC-13843 (Multi-turn guardrail) - delayed. Progress is blocked as the devs are busy supporting ai assistant get well plan 4\. WxCC-13953 (AI defense - extended guardrails) - delayed. likely to spill over into Q1
5 | Deliver Meaningful Product Differentiation and Velocity | Intelligent front door | Task Agent Orchestration Framework | 2026-05-27 14:02 | Month 2 | Jun 4 (June MBR) | Off Track/Delayed | No major productization work started on this beyond A2A / transfers | Active productization on this track will begin after we deliver the concierge framework
5 | Deliver Meaningful Product Differentiation and Velocity | Unlock team potential and development excellence | Accelerate SDLC changes in the age of AI including AI enablement for execution (knowledge for LLMs etc) | 2026-06-10 21:03 | Month 2 | Jun 4 (June MBR) | Complete |  | Dramatically reduced feature delivery time by over 50%. Average time spent for Discovery to Development went from 279 days to 130 days. This was primarily through cleanup and focused grooming workshops. | Confluence/tooling - CIscoIT approval, Budget
5 | Deliver Meaningful Product Differentiation and Velocity | Unlock team potential and development excellence | CPaaS: Use AI tools to drive efficiency | 2026-06-11 21:02 | Month 2 | Jun 4 (June MBR) | On Track | 100% | WxCoonnect & Gateway teams continued to delivered 50% story points. We are seeing potential to increase this further. We will revise this in Q1FY27. | None
5 | Deliver Meaningful Product Differentiation and Velocity | Unlock team potential and development excellence | Deliver media convergence | 2026-06-10 21:02 | Month 2 | Jun 4 (June MBR) | On Track | 2% | Development kicked off in both CC & Calling side. GA by FY27Q3.
5 | Deliver Meaningful Product Differentiation and Velocity | Unlock team potential and development excellence | Drive upskilling of teams through training and rotations (product knowledge, use of AI, new areas, etc.) | 2026-06-11 16:36 | Month 2 | Jun 4 (June MBR) | On Track | 60% | PM Training delivered, 100% of targeted PM rotation to new areas complete, use of AI in progress (~80% actively using AI) | Confluence/tooling - CIscoIT approval, Budget
5 | Deliver Meaningful Product Differentiation and Velocity | Unlock team potential and development excellence | Use AI tools to drive efficiency (WxCC, CCE) | 2026-06-10 21:25 | Month 2 | Jun 4 (June MBR) | On Track | 86% | 86% of code pull requests used GenAI in Q3. Teams continue to integrate AI into development processes.
6 | Strengthen Market Positioning and Routes to Market | Establish new and expand existing strategic technology partnerships | Establish process and governance for technology partnership decisions and approvals | 2026-06-08 08:01 | Month 2 | Jun 4 (June MBR) | On Track | On track | Taking slightly longer to implement than expected but no particular blockers, should be complete by end of June
6 | Strengthen Market Positioning and Routes to Market | Establish new and expand existing strategic technology partnerships | Expand and agree new GTM technology partnerships | 2026-06-08 08:01 | Month 2 | Jun 4 (June MBR) | On Track | On Track | Taking slightly longer to implement than expected but no particular blockers, should be complete by end of June
7 | Other | Address billing issues and reduce unbilled revenue | Reduce Unbilled revenue | 2026-06-08 08:05 | Month 2 | Jun 4 (June MBR) | On Track | April total = $2.59M Resolved = $1.15M New May = $1.89M May Total = $3.33M | Backlog improved but new May drove the increase | Obstacles overcome with Finance team providing timely updates and reports to all global teams.
7 | Other | Retain CPaaS run rate business | Shutdown legacy CPaaS platforms | 2026-06-04 10:38 | Month 2 | Jun 4 (June MBR) | On Track | Smarthub - Notify Shared environment customers have migrated Textlocal - Textlocal is now End of Sale, no more credits can be purchased, which should help the push to migrate final customers | Smart Hub - By end of July Q4 60% SH traffic will have migrated, 100% by end of Q1 Textlocal - Barclays to Campaign in progress and on track. Follow up comms to remaining customers in progress for final push to Interact. Preparation for decommissioning tasks is underway
| Not linked in Airtable | Not linked | Deliver impactful OneCisco experiences: CCaaS + UCaaS (reporting) | 2026-06-11 17:01 | Month 2 | Jun 4 (June MBR) | On Track |  | currently in EA, and expected to go GA by EOM/early july | Clarity on problem statements and business cases, Reciprocating support and prioritization, Commercial offer

## Airtable Record Comments
H2 Order | H2 Value | Record Type | Top-Level Method | Sub-Method | Comment Date | Author | Comment
No Airtable record comments extracted for this reporting-period update export.