## Summary
Jun 4 (June MBR) Updated Methods
Source | Live Airtable MCP
Base | CX FY26 V2MOM - NEW
Reporting Period | Jun 4 (June MBR)
Top-Level Update Records | 16
Supporting Update Records | 48
Total Update Records | 64
Generated At | 2026-06-10 13:05
Status | Count | Method Owner | Update Count
On Track | 35 | Manali Dongre | 7
At Risk | 14 | Brian Heikes | 6
Off Track/Delayed | 12 | Helen Briggs | 5
Planning | 2 | Karthik Sundaram | 5
Not specified | 1 | Krish Padmanabhan | 4
|  | Jitesh Gera | 3
|  | Manoj Muthavarapu | 3
|  | Nir Feldberg | 3
|  | Tim Hoolihan | 3
|  | Tom Clifford | 3
|  | Tristan Jewitt | 3
|  | Edu Moura | 2
|  | Kamesh Chidambaram | 2
|  | Martin King | 2
|  | Ravi Kiran Vadlamani | 2
|  | Abhiram Kramadhati | 1
|  | Chandramouli Vaithiyanathan | 1
|  | Charlotte Jewsbury | 1
|  | Dan Mathews | 1
|  | Girish Variyath | 1
|  | Jacq Hattingh | 1
|  | Kirsty Newsham | 1
|  | Marcus Quinn | 1
|  | Rama Krishna Balapalle | 1
|  | Sivacharan Bandi | 1
|  | Vinod Muthukrishnan | 1

## Combined Updates
Method Level | Method | Current Status | Method Owner | Status Owner | Update Date | Current Actual | Commentary
Supporting | Accelerate digital channel enablement (including functionality/ flow/ onboarding/ expansion)​ | At Risk | Manali Dongre | Manali Dongre | 2026-05-27 11:15 | 0 done | Out of 8 features - 7 in Development (3 in June, 1 in July, 3 GA in Sept). 1 in Planning Sept GA - Pause and Resume, Digital Data gaps, Channel type aggregation - large changes with significant data dependencies. Flow consolidation has multiple jiras. Not all are tracked here. This will flow into Q1 for GA.
Supporting | Address critical adminstrative experience gaps to address Gartner feedback (e.g., TMP, asset mgmt from connect, simplify setup, etc.)​ | At Risk | Brian Heikes | Brian Heikes | 2026-05-27 16:51 | 4 GA in H2 | Remaining FIRA of 6143 'Connect/Engage integration with CC and CCE' at risk due to dependencies. Teams working through planning to re-confirm dates and blockers.
Supporting | Close critical billing gaps (data pipeline, CPaaS)​ | At Risk | Brian Heikes | Brian Heikes | 2026-06-09 21:43 | 2 features delivered | LR impacts on Billing PM putting significant pressure on team to maintain momentum. Lack of Rev Assurance for CC means PM is spending significant time filling gaps with fewer people.
Supporting | Continue to drive best in class AI Agent voice experience | At Risk | Manoj Muthavarapu | Manoj Muthavarapu | 2026-05-27 14:00 | WxCC-11519 (S2S engine with AWS Novasonic) - Green WxCC-4562 (Soniox based AI engine for Concierge) - Amber WxCC-10394 (Voicea ASR for scripted agents) - Deprioritized | WxCC-11519 (S2S engine with AWS Novasonic) Further fixes based on early feedback done. This is in a good shape for CLUS demos but doesn't yet support multi-agent orchestration - that is the next milestone being targeted. WxCC-4562 (Soniox based AI engine for Concierge) - stretch feature Ready as a concierge engine but with the older 4.1-mini model. Early feedback showed that the conversational experience is good but the LLM responses are poor and flat (given the mini model). We were using this mainly to leverage PTUs but will now need to consider moving to 5.1-mini or abondon pursuing a pipeline based model for concierge and just stick to S2S models for concierge. Changing overall status to "At risk" to capture the GPS issue with Soniox and the contingency planning needed
Supporting | Define and execute structured in-life adoption motions | At Risk | Kamesh Chidambaram | Shreya Srinivas | 2026-06-02 11:34 | No change in customer coverage - 74% of all tech touch customers. New customer track yet to start. | Second email campaign delayed due to impacts to Marketing team. New date TBD.
Supporting | Deliver in-life management telemetry for AI | At Risk | Manali Dongre | Manali Dongre | 2026-05-27 12:18 | 1.5 features done | - AI Assistant in PowerBI - Done - Feature usage metrics - 90% of usage metrics needed by In-Life and Customer Success teams were available in Amplitude and PowerBI. There is a retention issue that is being worked on with WAP teams. - Operational metrics - 30% available in Amplitude and are made available. For remaining, approach being explored with the Data team to get the data into Splunk (since Platform team has moved Grafana metrics to Splunk and moving to Splunk is needed for TAC). Solution being explored to see whether reports need to be built in Splunk or PowerBI. Targeted for something in Q4 else will slip to Q1. However, PM driving this area was impacted and so looking to transition this to another PM
Supporting | Deliver native AI WEM (e.g., forecasting/scheduling maturity, reporting, intraday, call recording, etc.)​ | At Risk | Sivacharan Bandi | Manali Dongre | 2026-05-27 10:09 | 2 workloads GA (AI QM and AI Assistant) 1 workload in Beta (WFM) 2 workloads inprogress (AI Training, Performance Managemen) | Recording Management -Recording Management in Control Hub GA'd. Updated priorities based on field feedback on compliance recording. Will be working with engineering on those next. AI QM and AI Assistant workloads are GA. AI Agent GA WFM - Forecasting is in Beta (Estes is enabled). Scheduling has a few issues and can be demo'd with beta in Q4. Intraday Beta in July with GA for all in Q1 Performance Management - Agent Central first version will Beta in June with GA in August. AI training - Cisco Live Demo with Beta in Q1. GA will be Q2. Voice of Employee - Q1/Q2 Beta - Deferred until we get through some other workloads.
Supporting | Deliver new data capabilities including AI memory, context graph and JDS onboarding​ | At Risk | Manali Dongre | Manali Dongre | 2026-05-27 12:13 | 0 features | AI Memory: Cisco Live Demo on track. Early Access planned in July. GA in Q1FY27. Identity Management: Delayed to Q2FY27. Queue entity (2 features) - Need to remove from this method
Supporting | Dog and Pony Show | At Risk | Dan Mathews | Not specified | 2026-05-31 18:44 | Met with the account teams for all target GES opportunities and segmented them based on relationship and investment. SCG and COW are engaged in the investment accounts, but executive / GTM involvement is required in the majority of GES accounts to rebuild the relationship and capture mindshare.
Supporting | Deliver real time AI insights capabilities (e.g., create AI agent, etc.) ​ | Not specified | Manali Dongre | Manali Dongre | 2026-05-27 12:14 |  | Anomaly detection: At Cisco Live, WFM insights are being prioritized. Beta to come in August with GA in Q1FY2027. Topics -> Automation workflow: Team is heads down with multi-lingual and will work on this in parallel. Beta in July is hopeful. GA in Q1FY2027 However, if we decide to prioritize include Topics in the default license then the above will be impacted.
Supporting | Accelerate cloud migrations (401K) | Off Track/Delayed | Karthik Sundaram | Melissa Riner | 2026-06-09 15:41 | 2168 | Migration to the cloud is behind plan due to restrictive CCX offer criteria (75% of deals fail to qualify for the migration tool) and a lack of CCE-to-WxCC migration tool or incentives. The Collaboration GTM is currently revamping commercial offers to improve the value proposition and accelerate cloud adoption.
Supporting | Deliver approved market access initiatives - India | Off Track/Delayed | Kirsty Newsham | Kirsty Newsham | 2026-05-26 17:53 |  | India DC phase 2 - WebRTC. Delayed due to WxC dependency. Target GA has moved from July 26 to Oct 26. Amey has advised this cannot be delivered in Q4 but the team are assessing if they can deliver this earlier in Q1. India DC Phase 3 – Multi-Tenancy. At risk. Currently ranked as Priority 2.8; awaiting formal grooming to finalize technical requirements. Due to volume of work for admin this is at risk. We are currently reviewing trade-offs necessary to accelerate.
Supporting | Deliver enhancements to AI Agent Studio (e.g., Developer enablement, testing, AI engine, observability, security, knowledge, and CX desktop) | Off Track/Delayed | Manoj Muthavarapu | Manoj Muthavarapu | 2026-05-27 14:01 | Observability & Analytics - 3 on track, 1 slightly late and 1 delayed. AI engines - 1 deferred, 2 completed, 1 delayed Studio & dev experience - 1 completed, 1 on track, 2 late Knowledge - 2 late, 1 deprioritized, 1 added Security - 1 on track, 2 late | Observability 1\. WxCC-10723 (Observability metrics for Phase 1) - slightly late. Work is set to start from the coming sprint, but RBAC/date closure is still pending before this fully moves into DEV. 2\. WxCC-11721 (Observability dashboards) - on track. The dashboard shape is still moving forward, with RBAC and scope decisions being closed alongside the metrics work. 3\. WxCC-7711 (Simulated testing) - under active development. Team is keeping this on its current GA track and pushing net-new architecture work outside this FIRA. 4\. WxCC-6288 (Analyzer integration) - slightly late. GT is still being worked through and there are open data discrepancy issues to clear. 5\. WxCC-6232 (Transcript standardization / storage) - quite delayed. Service/version issues are still being worked through and the latest note was to avoid demoing this until after Cisco Live. AI engines 1\. WxCC-6290 (BYO AI engine) - deferred to Q1. 2\. WxCC-11669 (Pro-Europe engine) - completed / GA. 3\. WxCC-9986 (MCP support) - completed / GA. 4\. WxCC-9987 (Multi-agent orchestration with A2A) - delayed. mainly due to the prioritization of AI receptionist and AI assistant work items Studio & developer experience 1\. WxCC-6189 (AI optimized prompts) - on track. development continues. 2\. WxCC-8727 (Transfer actions) - running late. GA targeted for May 30 but multiple bugs discovered that need to be fixed. Feature is available to be turned on for select orgs as needed. 3\. WxCC-6525 (Custom event support) - completed / GA. 4\. WxCC-12767 (Sync timezone with org config) - delayed. should have been done in Q3 but has slipped into Q4 Knowledge 1\. WxCC-10649 (Knowledge aggregator integration) - deprioritized in favor of sharepoint connector 2\. WxCC-12314 (Many-to-many KB mapping / file download path) - slightly late. Still in capture and waiting for backend prioritization once higher-priority asks clear. 3\. WxCC-11936 (RAG ingestion improvements) - delayed but will be completed soon. Security 1\. WxCC-12925 (Guardrail controls) - cancelled. The original Jira is cancelled and this is now being folded into the broader AI Defense FIRA 2\. WxCC-11788 (AI defense - custom guardrails) - slightly late but ready for CLUS demos 3\. WxCC-13843 (Multi-turn guardrail) - delayed. Progress is blocked as the devs are busy supporting ai assistant get well plan 4\. WxCC-13953 (AI defense - extended guardrails) - delayed. likely to spill over into Q1
Supporting | Enhance reporting & analytics for AI products including ROI | Off Track/Delayed | Manali Dongre | Manali Dongre | 2026-05-27 12:16 | 0 features | Reporting for AI QM - Human Agent reports in Analyzer will be in June. For AI Agents planned for July beta. Reporting for AI Assistant - Delayed to Q1/Q2FY27 due to prioritizing AI Assistant Get Well Plan. Reporting for AI WFM - In Planning. Planned for Q1FY27 Analyzer feature - Comprehensive Home page on track for July GA. Analyzer feature - Streamlined create visualization - August/Sept beta. GA will be delayed to Q1FY27.
Supporting | Maintain product quality and availability [WxCCE] | Off Track/Delayed | Krish Padmanabhan | Suresh Hariharan | 2026-06-10 06:11 | May 2026 Platform Availability - 99.819% May 2026 Overall Availability - 99.986% | Platform availability impact due to DC outages (Almere and Denver) Platform availability has impacted a subset of customers (Geo based) and hence the variance Customer Escalations: 33 (SLA-5) (Cisco:14/ Part/Cust: 19) SLA impacting customers - Propharma(Wx011), Tesco(Wx019), Capgemini(Wx020), Portland General Electric(Wx043), Kaiser Permanente NCS(Wx054)
Supporting | Migrate CCE customers to Webex Contact Center using defined offers and tooling | Off Track/Delayed | Karthik Sundaram | Melissa Riner | 2026-06-09 15:54 | 1410 | Our cloud migration for renewed seats is currently tracking behind schedule. This is primarily driven by the lack of a CCE to WxCC migration tool and associated incentives. To address this challenge and accelerate cloud adoption, the Collaboration GTM team is evaluating our existing commercial offers and revamping our incentives to create a more compelling value proposition for our customers. Additionally, our vendor, Univnoix, is currently assessing the effort required to build a dedicated migration tool for CCE to WxCC.
Supporting | Migrate CCX customers to Webex Contact Center through partner-led motions | Off Track/Delayed | Karthik Sundaram | Melissa Riner | 2026-06-09 15:49 | 758 | City of Boston is first customer to go live with migration tool. The current migration offer is not achieving the intended outcomes. Until the GTM strategy and offer are updated, we anticipate continued challenges in driving improved results.
Supporting | Task Agent Orchestration Framework | Off Track/Delayed | Manoj Muthavarapu | Manoj Muthavarapu | 2026-05-27 14:02 | No major productization work started on this beyond A2A / transfers | Active productization on this track will begin after we deliver the concierge framework
Supporting | Turn active data into signals that power an insights-to-action architecture | Off Track/Delayed | Manali Dongre | Manali Dongre | 2026-05-27 12:12 | 0 features | Topic Analytics to apply to Digital and AI Agent interactions: Delayed to Q1FY27 due to dependency on transcripts for digital and AI Agent interactions aligning to a common format. Insights Orchestration: Demo for Cisco Live focused on WFM. Planned Beta for Q1FY27.
Supporting | AI Cookbooks | On Track | Chandramouli Vaithiyanathan | Maurice Lopes | 2026-06-02 20:33 |  | CookBook will be made public on Jun 5th
Supporting | Align marketing, sales, product, and partner orgs on vertical campaigns, messaging, content and targeted account lists - WxCC and AI | On Track | Helen Briggs | Not specified | 2026-05-12 11:00 | 5/12 - FY27 priorities being finalised this week in NY | 5/12 - H2 bridge plans in execution and FY27 priorities aligning key stakeholders in sales, partners, marketing progressing very well.
Supporting | Close remaining STC features | On Track | Manali Dongre | Betty Mai | 2026-05-27 11:08 | 2 features are GA (2374 and 5023) Remaining 2 features in Early Access (1272, 6128) with GA in June. | 2 features are GA (2374 and 5023) Remaining 2 features in Early Access (1272, 6128) with GA in June.
Supporting | Competitive takeout campaigns (e.g. Avaya, Genesys) | On Track | Jitesh Gera | Not specified | 2026-05-12 10:46 | 5/12 - Genesys Top 50 progressing. | 5/12 - Team cleaning data (CAV BU name vs SAV name) so that SFDC and Gong tracking can be done. GTM team cooordinating with SDR, as they have already been collaborating with an external agency to reach out to specific accounts. There was an ask to support a light touch approach on Five9s GES and large commercial customers but recent earnings were more positive than expected, so this is being de prioritised in Q4.
Supporting | Create One Cisco enterprise CX programs (including EA-based offers) | On Track | Tim Hoolihan | Not specified | 2026-05-12 11:02 | 5/12 - tied to overall Collaboration procing strategy work that Tim H and team are driving | 5/12 - looking to build offers to fit into existing buying models that are favourable with enterprise customers, eg EA3.0
Supporting | Deliver automation for repeatable FAQ use cases | On Track | Martin King | Not specified | 2026-06-04 10:34 | Knowledge Base Rate 51% | Increased as a result of more than 50% of Envoy ticket flow.​
Supporting | Deliver offers from product features that unblock enterprise deals | On Track | Tim Hoolihan | Not specified | 2026-05-12 10:49 | 5/12 - Product and GTM teams aligned, relevant offer go live plans in progress | 5/12 - No Q4 deal is blocked due to delayed offer availability
Supporting | Develop strategic portfolio pricing aligned to enterprise buying models | On Track | Tim Hoolihan | Not specified | 2026-05-12 10:51 | 5/12 - Tim Hoolihan successfully pivoting the teams to leverage customer preferred buying models | 5/12 - Offer team revising pricing strategies, moving away from BU silo'd approaches, to one that leverages EA3.0 and will build new offers to fit these customer preferred buying models
Supporting | Document and replicate successful expansion blueprints (white glove, events, executive engagement). | On Track | Edu Moura | Not specified | 2026-06-01 10:42 | We have successfully integrated WxCC into the CSM Lifecycle dashboard, including all playcards. We have booked an enablement session for June 10th to walk the Collaboration CSMs through these additions. | With our primary CoE playbook contact returning from paternity leave in June, we can move forward with exploring how to replicate the Playbook portal for the CSM team.
Supporting | Drive sustained Webex Contact Center adoption beyond go-live | On Track | Marcus Quinn | Marcus Quinn | 2026-06-09 09:34 | Q4 Total = 2 | Slow start to the Qtr - pushing the team to focus for next 2 months
Supporting | Enhance vertical focus on healthcare: EPIC integrations | On Track | Brian Heikes | Brian Heikes | 2026-05-27 16:48 | 1 Q4 feature GA | Pause/Resume recording support GA'd on May14, outbound dialer on track for late June.
Supporting | Establish process and governance for technology partnership decisions and approvals | On Track | Tom Clifford | Not specified | 2026-06-08 08:01 | On track | Taking slightly longer to implement than expected but no particular blockers, should be complete by end of June
Supporting | Execute renewals for existing contact center customers | On Track | Edu Moura | Edu Moura | 2026-06-03 02:08 | ​Q4 WxCC renewal is currently at 48.0% | ​Q4 WxCC renewal is currently at 48.0%, with 3,740 of 7,785 scoped seats renewed. The largest opportunity is the remaining renewal base: 2,871 seats across 101 accounts, representing $2.66M AOV still up for renewal.
Supporting | Expand and agree new GTM technology partnerships | On Track | Tom Clifford | Not specified | 2026-06-08 08:01 | On Track | Taking slightly longer to implement than expected but no particular blockers, should be complete by end of June
Supporting | Extend integrations with key ecosystem partners (Salesforce/Service Now) | On Track | Brian Heikes | Brian Heikes | 2026-05-27 17:06 | 1 (SCV live) | SCV live after offer/billing delay. Ongoing discussions on if BYOCCaaS Plan should be modified based on desire to keep routing on our platform - which would mean skipping planned BYO Phase 1.
Supporting | Launch AI routing capabilities | On Track | Brian Heikes | Brian Heikes | 2026-06-09 14:13 | Beta live, seeking additional customers.
Supporting | Launch sales plays for Cisco Calling customers | On Track | Charlotte Jewsbury | Not specified | 2026-06-01 11:31 |  | 1) kicked off activity with renewal team for opps to end FY27 >$50k AOV (approx 220 customers), any leads will be passed to CX specialists 2) finalised target list for FY28+ customers (approx 1400), kicked off work with Marketing to review list for outbound marketing activity - awaiting output & timeline
Supporting | Leverage Cisco’s broader installed base (networking, security, collaboration) to open CX doors. | On Track | Helen Briggs | Not specified | 2026-05-25 11:07 | 5/12 - Continued in progress | 5/12 - This is ongoing throughout the year - John Kiang and team continue to help identify which customers by SL1, SL2, SL3 ahave recently bought large networking, security, collaboration deals that may help sales engage and upsell CX.
Supporting | Maintain product quality and availability [CPaaS] | On Track | Rama Krishna Balapalle | Tim Strike | 2026-06-02 00:34 | 100% | May 100% platform availability, with two channel-impacting incidents with RCS delivery in US AWS and Azure environments
Supporting | Maintain product quality and availability [WxCC] | On Track | Ravi Kiran Vadlamani | Marie Prentice | 2026-06-09 16:55 | 99.995%​ | Availability was impacted by two P1 incidents that affected US Prod1.
Supporting | Maintain product quality and availability [WxCCE] | On Track | Krish Padmanabhan | Suresh Hariharan | 2026-06-02 10:30 | May SLA uptime - 99.995% Platform - 100%
Supporting | Maintain product quality for on-prem customers | On Track | Krish Padmanabhan | Suresh Hariharan | 2026-06-02 10:31 | No active CAP or Hotsite | Verizon issue was handled well and appreciated by Customer and Accounts team
Supporting | Maintain product quality for on-prem customers | On Track | Krish Padmanabhan | Suresh Hariharan | 2026-06-10 06:15 | No active CAP or Hotsite | Verizon issue was handled well and appreciated by Customer and Accounts team
Supporting | Nutanix hypervisor support for CCE | On Track | Girish Variyath | Girish Variyath | 2026-06-10 08:56 | GA on track - planned for end Q4FY26 | Beta in progress: HCSC, T-Mobile, Keck
Supporting | Reduce Unbilled revenue | On Track | Jacq Hattingh | Jacq Hattingh | 2026-06-08 08:05 | April total = $2.59M Resolved = $1.15M New May = $1.89M May Total = $3.33M | Backlog improved but new May drove the increase
Supporting | Reduce zero-usage Cloud Contact Center customers | On Track | Kamesh Chidambaram | Kamesh Chidambaram | 2026-06-09 09:32 | 86 Tenants | No usage tenants count stands at 86 tenants (6%), compared to 106 tenants (7%) at end Q3​
Supporting | Shutdown legacy CPaaS platforms | On Track | Nir Feldberg | Not specified | 2026-06-04 10:38 | Smarthub - Notify Shared environment customers have migrated Textlocal - Textlocal is now End of Sale, no more credits can be purchased, which should help the push to migrate final customers | Smart Hub - By end of July Q4 60% SH traffic will have migrated, 100% by end of Q1 Textlocal - Barclays to Campaign in progress and on track. Follow up comms to remaining customers in progress for final push to Interact. Preparation for decommissioning tasks is underway
Supporting | Incentivise and upgrade CCX base to R15.0 | Planning | Karthik Sundaram | Maurice Lopes | 2026-06-09 15:43 | N/A | We are partnering with IT and Webex Analytics to build a dedicated dashboard for on-prem R15 upgrades. This tool will utilize smart licensing data to resolve current visibility gaps and allow for clear segmentation between UCCX and UCCE.
Supporting | Multi-Region Disaster Recovery for Webex Contact Center | Planning | Brian Heikes | Not specified | 2026-05-27 16:55 | Planning | Planning underway, but may need prioritization calls on if we have to make tradeoffs to hit timeline.
Top-Level | Drive expansion of Webex Contact Center | At Risk | Tristan Jewitt | Kamesh Chidambaram | 2026-06-03 02:12 | 2 WxCC opportunities | Only 2 opportunities raised so far against target of 25 in Q4. However, we exceeded target in Q3 at 35.
Top-Level | Execute disciplined migration from on-prem to Webex Contact Center | At Risk | Karthik Sundaram | Maurice Lopes | 2026-06-03 12:05 | 3.7% (1.0K / 27K)
Top-Level | Protect and grow renewal revenue in the installed base | At Risk | Jitesh Gera | Not specified | 2026-06-03 12:08 | 54% renewed from Q4M1 ATR (14.8k from 27.4k) 902.7k seats | 42% of Q4 ATR renewed, 13% lost, 6% downsell, 42% still available to be renewed.
Top-Level | Reduce operational friction through in-life automation | At Risk | Martin King | Not specified | 2026-06-04 10:31 | 72.4% | Need for Human support rate increased due to high failure rates on Webex Campaign and Notify
Top-Level | Unblock enterprise deals through product and pricing | At Risk | Helen Briggs | Not specified | 2026-06-03 12:12 | 2 deals >= 1k seats 1.3K greenfield seats | 2 deals, DSV & MakeMyTrip booked 10,00 seats in M9.
Top-Level | Grow the Cloud Contact Center business | Off Track/Delayed | Vinod Muthukrishnan | Jason Wemyss | 2026-06-03 12:16 | Q4M1 Close - 185k seats
Top-Level | Make AI easy to start and hard to abandon | Off Track/Delayed | Abhiram Kramadhati | Maurice Lopes | 2026-06-03 12:14 | **WxCC Installed base:** \- AI Agent: 10% \- AI Assistant: 10% \- Overall Attach: 13% **New orders:** \- AI Agent: 20% \- AI Assistant: 13% \- Overall Attach: 24% | Cisco attach and adoption challenges are primarily due to Offer Setup, Positioning and Coverage challenges. Next steps: GTM plan for better AI positioning and coverage. Product plan to support with pre-built use cases and vertical focus.
Top-Level | Unblock enterprise deals through product and pricing | Off Track/Delayed | Helen Briggs | Not specified | 2026-05-12 10:30 | 5/12 - 0 deals booked and only 117 greenfield seats booked QTD. YTD, there are 0 deals booked with >1000 seats and 1,447 greenfield seats booked vs target of 40k. | 5/12 - Entergy deal was lost to Genesys, Providence is still a Q4 opportunity expected to close in Q4.
Top-Level | Address billing issues and reduce unbilled revenue | On Track | Nir Feldberg | Not specified | 2026-06-08 08:11 | April total = $2.59M Resolved = $1.15M New May = $1.89M May Total = $3.33M | Backlog improved but new may drove the increase
Top-Level | Drive post-sale adoption as a core operating motion | On Track | Tristan Jewitt | Kamesh Chidambaram | 2026-06-09 09:33 | 86 Accounts | No usage tenants count stands at 86 tenants (6%), compared to 106 tenants (7%) at end Q3​
Top-Level | Establish new and expand existing strategic technology partnerships | On Track | Tom Clifford | Not specified | 2026-06-08 08:00 | On Track | Taking slightly longer to implement than expected but no particular blockers, should be complete by end of June
Top-Level | Expand enterprise demand through adjacency and One Cisco motions | On Track | Helen Briggs | Not specified | 2026-05-12 11:04 | 5/12 - FY27 plan should be finalised followng this weeks meetings in NY | 5/12 - FY27 Collaboration Product GTM plan focuses on 3 pillars: 1. AI Attach 2. Grow Devices business by 100% 3. Foundational
Top-Level | Improve CX renewal rates and contract duration | On Track | Tristan Jewitt | Not specified | 2026-06-03 02:10 | ​Q4 WxCC renewal is currently at 48.0% | ​Q4 WxCC renewal is currently at 48.0%, with 3,740 of 7,785 scoped seats renewed. The largest opportunity is the remaining renewal base: 2,871 seats across 101 accounts, representing $2.66M AOV still up for renewal.
Top-Level | Maintain product quality and availability | On Track | Ravi Kiran Vadlamani | Marie Prentice | 2026-06-09 20:26 | WxCCE: May SLA uptime - 99.995%, Platform - 100%, 0 CAP / 0 Hot WxCC: May Global 99.995% CPaaS: May 100% Platform Availability | Availability in May showed strong performance across the portfolio. WxCCE achieved a May SLA uptime of 99.995% with platform availability at 100%, reporting no CAP or Hot Site issues. A Verizon-related incident was managed effectively and received positive feedback from both the Customer and Accounts teams. WxCC recorded a global availability of 99.995%, though impacted by two P1 incidents affecting the US Prod1 environment. CPaaS maintained 100% platform availability despite experiencing two channel-impacting incidents related to RCS delivery in the US AWS and Azure environments.
Top-Level | Protect and grow renewal revenue in the installed base | On Track | Jitesh Gera | Not specified | 2026-05-12 10:24 | 5/12 - 75% (102k of 137k ATR) have renewed, with 5% (5.6k of 102k) migrating to cloud. YTD, 73% of FY26 ATR has renewed, with 4% migrating to cloud. | 5/12 - caught up and exceeding the q4 renewal target of 73%, still striving to achieve the H2 Bridge plan stretch target of 79% renewing. The cloud migration target is still unlikely to be achieved though.
Top-Level | Retain CPaaS run rate business | On Track | Nir Feldberg | Tristan Jewitt | 2026-06-09 10:49 | •108% revenue growth existing customers •100% retention >$100k customers | On track to exceed the 105% revenue growth target

## Top-Level Updates
Method Level | Method | Current Status | Method Owner | Status Owner | Update Date | Current Actual | Commentary
Top-Level | Reduce operational friction through in-life automation | At Risk | Martin King | Not specified | 2026-06-04 10:31 | 72.4% | Need for Human support rate increased due to high failure rates on Webex Campaign and Notify
Top-Level | Expand enterprise demand through adjacency and One Cisco motions | On Track | Helen Briggs | Not specified | 2026-05-12 11:04 | 5/12 - FY27 plan should be finalised followng this weeks meetings in NY | 5/12 - FY27 Collaboration Product GTM plan focuses on 3 pillars: 1. AI Attach 2. Grow Devices business by 100% 3. Foundational
Top-Level | Maintain product quality and availability | On Track | Ravi Kiran Vadlamani | Marie Prentice | 2026-06-09 20:26 | WxCCE: May SLA uptime - 99.995%, Platform - 100%, 0 CAP / 0 Hot WxCC: May Global 99.995% CPaaS: May 100% Platform Availability | Availability in May showed strong performance across the portfolio. WxCCE achieved a May SLA uptime of 99.995% with platform availability at 100%, reporting no CAP or Hot Site issues. A Verizon-related incident was managed effectively and received positive feedback from both the Customer and Accounts teams. WxCC recorded a global availability of 99.995%, though impacted by two P1 incidents affecting the US Prod1 environment. CPaaS maintained 100% platform availability despite experiencing two channel-impacting incidents related to RCS delivery in the US AWS and Azure environments.
Top-Level | Make AI easy to start and hard to abandon | Off Track/Delayed | Abhiram Kramadhati | Maurice Lopes | 2026-06-03 12:14 | **WxCC Installed base:** \- AI Agent: 10% \- AI Assistant: 10% \- Overall Attach: 13% **New orders:** \- AI Agent: 20% \- AI Assistant: 13% \- Overall Attach: 24% | Cisco attach and adoption challenges are primarily due to Offer Setup, Positioning and Coverage challenges. Next steps: GTM plan for better AI positioning and coverage. Product plan to support with pre-built use cases and vertical focus.
Top-Level | Establish new and expand existing strategic technology partnerships | On Track | Tom Clifford | Not specified | 2026-06-08 08:00 | On Track | Taking slightly longer to implement than expected but no particular blockers, should be complete by end of June
Top-Level | Drive expansion of Webex Contact Center | At Risk | Tristan Jewitt | Kamesh Chidambaram | 2026-06-03 02:12 | 2 WxCC opportunities | Only 2 opportunities raised so far against target of 25 in Q4. However, we exceeded target in Q3 at 35.
Top-Level | Unblock enterprise deals through product and pricing | At Risk | Helen Briggs | Not specified | 2026-06-03 12:12 | 2 deals >= 1k seats 1.3K greenfield seats | 2 deals, DSV & MakeMyTrip booked 10,00 seats in M9.
Top-Level | Address billing issues and reduce unbilled revenue | On Track | Nir Feldberg | Not specified | 2026-06-08 08:11 | April total = $2.59M Resolved = $1.15M New May = $1.89M May Total = $3.33M | Backlog improved but new may drove the increase
Top-Level | Improve CX renewal rates and contract duration | On Track | Tristan Jewitt | Not specified | 2026-06-03 02:10 | ​Q4 WxCC renewal is currently at 48.0% | ​Q4 WxCC renewal is currently at 48.0%, with 3,740 of 7,785 scoped seats renewed. The largest opportunity is the remaining renewal base: 2,871 seats across 101 accounts, representing $2.66M AOV still up for renewal.
Top-Level | Grow the Cloud Contact Center business | Off Track/Delayed | Vinod Muthukrishnan | Jason Wemyss | 2026-06-03 12:16 | Q4M1 Close - 185k seats
Top-Level | Protect and grow renewal revenue in the installed base | At Risk | Jitesh Gera | Not specified | 2026-06-03 12:08 | 54% renewed from Q4M1 ATR (14.8k from 27.4k) 902.7k seats | 42% of Q4 ATR renewed, 13% lost, 6% downsell, 42% still available to be renewed.
Top-Level | Execute disciplined migration from on-prem to Webex Contact Center | At Risk | Karthik Sundaram | Maurice Lopes | 2026-06-03 12:05 | 3.7% (1.0K / 27K)
Top-Level | Protect and grow renewal revenue in the installed base | On Track | Jitesh Gera | Not specified | 2026-05-12 10:24 | 5/12 - 75% (102k of 137k ATR) have renewed, with 5% (5.6k of 102k) migrating to cloud. YTD, 73% of FY26 ATR has renewed, with 4% migrating to cloud. | 5/12 - caught up and exceeding the q4 renewal target of 73%, still striving to achieve the H2 Bridge plan stretch target of 79% renewing. The cloud migration target is still unlikely to be achieved though.
Top-Level | Retain CPaaS run rate business | On Track | Nir Feldberg | Tristan Jewitt | 2026-06-09 10:49 | •108% revenue growth existing customers •100% retention >$100k customers | On track to exceed the 105% revenue growth target
Top-Level | Drive post-sale adoption as a core operating motion | On Track | Tristan Jewitt | Kamesh Chidambaram | 2026-06-09 09:33 | 86 Accounts | No usage tenants count stands at 86 tenants (6%), compared to 106 tenants (7%) at end Q3​
Top-Level | Unblock enterprise deals through product and pricing | Off Track/Delayed | Helen Briggs | Not specified | 2026-05-12 10:30 | 5/12 - 0 deals booked and only 117 greenfield seats booked QTD. YTD, there are 0 deals booked with >1000 seats and 1,447 greenfield seats booked vs target of 40k. | 5/12 - Entergy deal was lost to Genesys, Providence is still a Q4 opportunity expected to close in Q4.

## Supporting Updates
Method Level | Method | Current Status | Method Owner | Status Owner | Update Date | Current Actual | Commentary
Supporting | Expand and agree new GTM technology partnerships | On Track | Tom Clifford | Not specified | 2026-06-08 08:01 | On Track | Taking slightly longer to implement than expected but no particular blockers, should be complete by end of June
Supporting | Establish process and governance for technology partnership decisions and approvals | On Track | Tom Clifford | Not specified | 2026-06-08 08:01 | On track | Taking slightly longer to implement than expected but no particular blockers, should be complete by end of June
Supporting | Continue to drive best in class AI Agent voice experience | At Risk | Manoj Muthavarapu | Manoj Muthavarapu | 2026-05-27 14:00 | WxCC-11519 (S2S engine with AWS Novasonic) - Green WxCC-4562 (Soniox based AI engine for Concierge) - Amber WxCC-10394 (Voicea ASR for scripted agents) - Deprioritized | WxCC-11519 (S2S engine with AWS Novasonic) Further fixes based on early feedback done. This is in a good shape for CLUS demos but doesn't yet support multi-agent orchestration - that is the next milestone being targeted. WxCC-4562 (Soniox based AI engine for Concierge) - stretch feature Ready as a concierge engine but with the older 4.1-mini model. Early feedback showed that the conversational experience is good but the LLM responses are poor and flat (given the mini model). We were using this mainly to leverage PTUs but will now need to consider moving to 5.1-mini or abondon pursuing a pipeline based model for concierge and just stick to S2S models for concierge. Changing overall status to "At risk" to capture the GPS issue with Soniox and the contingency planning needed
Supporting | Maintain product quality and availability [CPaaS] | On Track | Rama Krishna Balapalle | Tim Strike | 2026-06-02 00:34 | 100% | May 100% platform availability, with two channel-impacting incidents with RCS delivery in US AWS and Azure environments
Supporting | Multi-Region Disaster Recovery for Webex Contact Center | Planning | Brian Heikes | Not specified | 2026-05-27 16:55 | Planning | Planning underway, but may need prioritization calls on if we have to make tradeoffs to hit timeline.
Supporting | Align marketing, sales, product, and partner orgs on vertical campaigns, messaging, content and targeted account lists - WxCC and AI | On Track | Helen Briggs | Not specified | 2026-05-12 11:00 | 5/12 - FY27 priorities being finalised this week in NY | 5/12 - H2 bridge plans in execution and FY27 priorities aligning key stakeholders in sales, partners, marketing progressing very well.
Supporting | Close remaining STC features | On Track | Manali Dongre | Betty Mai | 2026-05-27 11:08 | 2 features are GA (2374 and 5023) Remaining 2 features in Early Access (1272, 6128) with GA in June. | 2 features are GA (2374 and 5023) Remaining 2 features in Early Access (1272, 6128) with GA in June.
Supporting | Reduce Unbilled revenue | On Track | Jacq Hattingh | Jacq Hattingh | 2026-06-08 08:05 | April total = $2.59M Resolved = $1.15M New May = $1.89M May Total = $3.33M | Backlog improved but new May drove the increase
Supporting | Launch sales plays for Cisco Calling customers | On Track | Charlotte Jewsbury | Not specified | 2026-06-01 11:31 |  | 1) kicked off activity with renewal team for opps to end FY27 >$50k AOV (approx 220 customers), any leads will be passed to CX specialists 2) finalised target list for FY28+ customers (approx 1400), kicked off work with Marketing to review list for outbound marketing activity - awaiting output & timeline
Supporting | Deliver automation for repeatable FAQ use cases | On Track | Martin King | Not specified | 2026-06-04 10:34 | Knowledge Base Rate 51% | Increased as a result of more than 50% of Envoy ticket flow.​
Supporting | Deliver native AI WEM (e.g., forecasting/scheduling maturity, reporting, intraday, call recording, etc.)​ | At Risk | Sivacharan Bandi | Manali Dongre | 2026-05-27 10:09 | 2 workloads GA (AI QM and AI Assistant) 1 workload in Beta (WFM) 2 workloads inprogress (AI Training, Performance Managemen) | Recording Management -Recording Management in Control Hub GA'd. Updated priorities based on field feedback on compliance recording. Will be working with engineering on those next. AI QM and AI Assistant workloads are GA. AI Agent GA WFM - Forecasting is in Beta (Estes is enabled). Scheduling has a few issues and can be demo'd with beta in Q4. Intraday Beta in July with GA for all in Q1 Performance Management - Agent Central first version will Beta in June with GA in August. AI training - Cisco Live Demo with Beta in Q1. GA will be Q2. Voice of Employee - Q1/Q2 Beta - Deferred until we get through some other workloads.
Supporting | Dog and Pony Show | At Risk | Dan Mathews | Not specified | 2026-05-31 18:44 | Met with the account teams for all target GES opportunities and segmented them based on relationship and investment. SCG and COW are engaged in the investment accounts, but executive / GTM involvement is required in the majority of GES accounts to rebuild the relationship and capture mindshare.
Supporting | Extend integrations with key ecosystem partners (Salesforce/Service Now) | On Track | Brian Heikes | Brian Heikes | 2026-05-27 17:06 | 1 (SCV live) | SCV live after offer/billing delay. Ongoing discussions on if BYOCCaaS Plan should be modified based on desire to keep routing on our platform - which would mean skipping planned BYO Phase 1.
Supporting | Close critical billing gaps (data pipeline, CPaaS)​ | At Risk | Brian Heikes | Brian Heikes | 2026-06-09 21:43 | 2 features delivered | LR impacts on Billing PM putting significant pressure on team to maintain momentum. Lack of Rev Assurance for CC means PM is spending significant time filling gaps with fewer people.
Supporting | Reduce zero-usage Cloud Contact Center customers | On Track | Kamesh Chidambaram | Kamesh Chidambaram | 2026-06-09 09:32 | 86 Tenants | No usage tenants count stands at 86 tenants (6%), compared to 106 tenants (7%) at end Q3​
Supporting | AI Cookbooks | On Track | Chandramouli Vaithiyanathan | Maurice Lopes | 2026-06-02 20:33 |  | CookBook will be made public on Jun 5th
Supporting | Execute renewals for existing contact center customers | On Track | Edu Moura | Edu Moura | 2026-06-03 02:08 | ​Q4 WxCC renewal is currently at 48.0% | ​Q4 WxCC renewal is currently at 48.0%, with 3,740 of 7,785 scoped seats renewed. The largest opportunity is the remaining renewal base: 2,871 seats across 101 accounts, representing $2.66M AOV still up for renewal.
Supporting | Create One Cisco enterprise CX programs (including EA-based offers) | On Track | Tim Hoolihan | Not specified | 2026-05-12 11:02 | 5/12 - tied to overall Collaboration procing strategy work that Tim H and team are driving | 5/12 - looking to build offers to fit into existing buying models that are favourable with enterprise customers, eg EA3.0
Supporting | Turn active data into signals that power an insights-to-action architecture | Off Track/Delayed | Manali Dongre | Manali Dongre | 2026-05-27 12:12 | 0 features | Topic Analytics to apply to Digital and AI Agent interactions: Delayed to Q1FY27 due to dependency on transcripts for digital and AI Agent interactions aligning to a common format. Insights Orchestration: Demo for Cisco Live focused on WFM. Planned Beta for Q1FY27.
Supporting | Define and execute structured in-life adoption motions | At Risk | Kamesh Chidambaram | Shreya Srinivas | 2026-06-02 11:34 | No change in customer coverage - 74% of all tech touch customers. New customer track yet to start. | Second email campaign delayed due to impacts to Marketing team. New date TBD.
Supporting | Enhance vertical focus on healthcare: EPIC integrations | On Track | Brian Heikes | Brian Heikes | 2026-05-27 16:48 | 1 Q4 feature GA | Pause/Resume recording support GA'd on May14, outbound dialer on track for late June.
Supporting | Deliver in-life management telemetry for AI | At Risk | Manali Dongre | Manali Dongre | 2026-05-27 12:18 | 1.5 features done | - AI Assistant in PowerBI - Done - Feature usage metrics - 90% of usage metrics needed by In-Life and Customer Success teams were available in Amplitude and PowerBI. There is a retention issue that is being worked on with WAP teams. - Operational metrics - 30% available in Amplitude and are made available. For remaining, approach being explored with the Data team to get the data into Splunk (since Platform team has moved Grafana metrics to Splunk and moving to Splunk is needed for TAC). Solution being explored to see whether reports need to be built in Splunk or PowerBI. Targeted for something in Q4 else will slip to Q1. However, PM driving this area was impacted and so looking to transition this to another PM
Supporting | Document and replicate successful expansion blueprints (white glove, events, executive engagement). | On Track | Edu Moura | Not specified | 2026-06-01 10:42 | We have successfully integrated WxCC into the CSM Lifecycle dashboard, including all playcards. We have booked an enablement session for June 10th to walk the Collaboration CSMs through these additions. | With our primary CoE playbook contact returning from paternity leave in June, we can move forward with exploring how to replicate the Playbook portal for the CSM team.
Supporting | Maintain product quality and availability [WxCC] | On Track | Ravi Kiran Vadlamani | Marie Prentice | 2026-06-09 16:55 | 99.995%​ | Availability was impacted by two P1 incidents that affected US Prod1.
Supporting | Accelerate digital channel enablement (including functionality/ flow/ onboarding/ expansion)​ | At Risk | Manali Dongre | Manali Dongre | 2026-05-27 11:15 | 0 done | Out of 8 features - 7 in Development (3 in June, 1 in July, 3 GA in Sept). 1 in Planning Sept GA - Pause and Resume, Digital Data gaps, Channel type aggregation - large changes with significant data dependencies. Flow consolidation has multiple jiras. Not all are tracked here. This will flow into Q1 for GA.
Supporting | Shutdown legacy CPaaS platforms | On Track | Nir Feldberg | Not specified | 2026-06-04 10:38 | Smarthub - Notify Shared environment customers have migrated Textlocal - Textlocal is now End of Sale, no more credits can be purchased, which should help the push to migrate final customers | Smart Hub - By end of July Q4 60% SH traffic will have migrated, 100% by end of Q1 Textlocal - Barclays to Campaign in progress and on track. Follow up comms to remaining customers in progress for final push to Interact. Preparation for decommissioning tasks is underway
Supporting | Enhance reporting & analytics for AI products including ROI | Off Track/Delayed | Manali Dongre | Manali Dongre | 2026-05-27 12:16 | 0 features | Reporting for AI QM - Human Agent reports in Analyzer will be in June. For AI Agents planned for July beta. Reporting for AI Assistant - Delayed to Q1/Q2FY27 due to prioritizing AI Assistant Get Well Plan. Reporting for AI WFM - In Planning. Planned for Q1FY27 Analyzer feature - Comprehensive Home page on track for July GA. Analyzer feature - Streamlined create visualization - August/Sept beta. GA will be delayed to Q1FY27.
Supporting | Incentivise and upgrade CCX base to R15.0 | Planning | Karthik Sundaram | Maurice Lopes | 2026-06-09 15:43 | N/A | We are partnering with IT and Webex Analytics to build a dedicated dashboard for on-prem R15 upgrades. This tool will utilize smart licensing data to resolve current visibility gaps and allow for clear segmentation between UCCX and UCCE.
Supporting | Migrate CCE customers to Webex Contact Center using defined offers and tooling | Off Track/Delayed | Karthik Sundaram | Melissa Riner | 2026-06-09 15:54 | 1410 | Our cloud migration for renewed seats is currently tracking behind schedule. This is primarily driven by the lack of a CCE to WxCC migration tool and associated incentives. To address this challenge and accelerate cloud adoption, the Collaboration GTM team is evaluating our existing commercial offers and revamping our incentives to create a more compelling value proposition for our customers. Additionally, our vendor, Univnoix, is currently assessing the effort required to build a dedicated migration tool for CCE to WxCC.
Supporting | Maintain product quality for on-prem customers | On Track | Krish Padmanabhan | Suresh Hariharan | 2026-06-02 10:31 | No active CAP or Hotsite | Verizon issue was handled well and appreciated by Customer and Accounts team
Supporting | Launch AI routing capabilities | On Track | Brian Heikes | Brian Heikes | 2026-06-09 14:13 | Beta live, seeking additional customers.
Supporting | Deliver approved market access initiatives - India | Off Track/Delayed | Kirsty Newsham | Kirsty Newsham | 2026-05-26 17:53 |  | India DC phase 2 - WebRTC. Delayed due to WxC dependency. Target GA has moved from July 26 to Oct 26. Amey has advised this cannot be delivered in Q4 but the team are assessing if they can deliver this earlier in Q1. India DC Phase 3 – Multi-Tenancy. At risk. Currently ranked as Priority 2.8; awaiting formal grooming to finalize technical requirements. Due to volume of work for admin this is at risk. We are currently reviewing trade-offs necessary to accelerate.
Supporting | Nutanix hypervisor support for CCE | On Track | Girish Variyath | Girish Variyath | 2026-06-10 08:56 | GA on track - planned for end Q4FY26 | Beta in progress: HCSC, T-Mobile, Keck
Supporting | Deliver new data capabilities including AI memory, context graph and JDS onboarding​ | At Risk | Manali Dongre | Manali Dongre | 2026-05-27 12:13 | 0 features | AI Memory: Cisco Live Demo on track. Early Access planned in July. GA in Q1FY27. Identity Management: Delayed to Q2FY27. Queue entity (2 features) - Need to remove from this method
Supporting | Maintain product quality and availability [WxCCE] | Off Track/Delayed | Krish Padmanabhan | Suresh Hariharan | 2026-06-10 06:11 | May 2026 Platform Availability - 99.819% May 2026 Overall Availability - 99.986% | Platform availability impact due to DC outages (Almere and Denver) Platform availability has impacted a subset of customers (Geo based) and hence the variance Customer Escalations: 33 (SLA-5) (Cisco:14/ Part/Cust: 19) SLA impacting customers - Propharma(Wx011), Tesco(Wx019), Capgemini(Wx020), Portland General Electric(Wx043), Kaiser Permanente NCS(Wx054)
Supporting | Drive sustained Webex Contact Center adoption beyond go-live | On Track | Marcus Quinn | Marcus Quinn | 2026-06-09 09:34 | Q4 Total = 2 | Slow start to the Qtr - pushing the team to focus for next 2 months
Supporting | Competitive takeout campaigns (e.g. Avaya, Genesys) | On Track | Jitesh Gera | Not specified | 2026-05-12 10:46 | 5/12 - Genesys Top 50 progressing. | 5/12 - Team cleaning data (CAV BU name vs SAV name) so that SFDC and Gong tracking can be done. GTM team cooordinating with SDR, as they have already been collaborating with an external agency to reach out to specific accounts. There was an ask to support a light touch approach on Five9s GES and large commercial customers but recent earnings were more positive than expected, so this is being de prioritised in Q4.
Supporting | Deliver real time AI insights capabilities (e.g., create AI agent, etc.) ​ | Not specified | Manali Dongre | Manali Dongre | 2026-05-27 12:14 |  | Anomaly detection: At Cisco Live, WFM insights are being prioritized. Beta to come in August with GA in Q1FY2027. Topics -> Automation workflow: Team is heads down with multi-lingual and will work on this in parallel. Beta in July is hopeful. GA in Q1FY2027 However, if we decide to prioritize include Topics in the default license then the above will be impacted.
Supporting | Deliver enhancements to AI Agent Studio (e.g., Developer enablement, testing, AI engine, observability, security, knowledge, and CX desktop) | Off Track/Delayed | Manoj Muthavarapu | Manoj Muthavarapu | 2026-05-27 14:01 | Observability & Analytics - 3 on track, 1 slightly late and 1 delayed. AI engines - 1 deferred, 2 completed, 1 delayed Studio & dev experience - 1 completed, 1 on track, 2 late Knowledge - 2 late, 1 deprioritized, 1 added Security - 1 on track, 2 late | Observability 1\. WxCC-10723 (Observability metrics for Phase 1) - slightly late. Work is set to start from the coming sprint, but RBAC/date closure is still pending before this fully moves into DEV. 2\. WxCC-11721 (Observability dashboards) - on track. The dashboard shape is still moving forward, with RBAC and scope decisions being closed alongside the metrics work. 3\. WxCC-7711 (Simulated testing) - under active development. Team is keeping this on its current GA track and pushing net-new architecture work outside this FIRA. 4\. WxCC-6288 (Analyzer integration) - slightly late. GT is still being worked through and there are open data discrepancy issues to clear. 5\. WxCC-6232 (Transcript standardization / storage) - quite delayed. Service/version issues are still being worked through and the latest note was to avoid demoing this until after Cisco Live. AI engines 1\. WxCC-6290 (BYO AI engine) - deferred to Q1. 2\. WxCC-11669 (Pro-Europe engine) - completed / GA. 3\. WxCC-9986 (MCP support) - completed / GA. 4\. WxCC-9987 (Multi-agent orchestration with A2A) - delayed. mainly due to the prioritization of AI receptionist and AI assistant work items Studio & developer experience 1\. WxCC-6189 (AI optimized prompts) - on track. development continues. 2\. WxCC-8727 (Transfer actions) - running late. GA targeted for May 30 but multiple bugs discovered that need to be fixed. Feature is available to be turned on for select orgs as needed. 3\. WxCC-6525 (Custom event support) - completed / GA. 4\. WxCC-12767 (Sync timezone with org config) - delayed. should have been done in Q3 but has slipped into Q4 Knowledge 1\. WxCC-10649 (Knowledge aggregator integration) - deprioritized in favor of sharepoint connector 2\. WxCC-12314 (Many-to-many KB mapping / file download path) - slightly late. Still in capture and waiting for backend prioritization once higher-priority asks clear. 3\. WxCC-11936 (RAG ingestion improvements) - delayed but will be completed soon. Security 1\. WxCC-12925 (Guardrail controls) - cancelled. The original Jira is cancelled and this is now being folded into the broader AI Defense FIRA 2\. WxCC-11788 (AI defense - custom guardrails) - slightly late but ready for CLUS demos 3\. WxCC-13843 (Multi-turn guardrail) - delayed. Progress is blocked as the devs are busy supporting ai assistant get well plan 4\. WxCC-13953 (AI defense - extended guardrails) - delayed. likely to spill over into Q1
Supporting | Accelerate cloud migrations (401K) | Off Track/Delayed | Karthik Sundaram | Melissa Riner | 2026-06-09 15:41 | 2168 | Migration to the cloud is behind plan due to restrictive CCX offer criteria (75% of deals fail to qualify for the migration tool) and a lack of CCE-to-WxCC migration tool or incentives. The Collaboration GTM is currently revamping commercial offers to improve the value proposition and accelerate cloud adoption.
Supporting | Maintain product quality for on-prem customers | On Track | Krish Padmanabhan | Suresh Hariharan | 2026-06-10 06:15 | No active CAP or Hotsite | Verizon issue was handled well and appreciated by Customer and Accounts team
Supporting | Develop strategic portfolio pricing aligned to enterprise buying models | On Track | Tim Hoolihan | Not specified | 2026-05-12 10:51 | 5/12 - Tim Hoolihan successfully pivoting the teams to leverage customer preferred buying models | 5/12 - Offer team revising pricing strategies, moving away from BU silo'd approaches, to one that leverages EA3.0 and will build new offers to fit these customer preferred buying models
Supporting | Address critical adminstrative experience gaps to address Gartner feedback (e.g., TMP, asset mgmt from connect, simplify setup, etc.)​ | At Risk | Brian Heikes | Brian Heikes | 2026-05-27 16:51 | 4 GA in H2 | Remaining FIRA of 6143 'Connect/Engage integration with CC and CCE' at risk due to dependencies. Teams working through planning to re-confirm dates and blockers.
Supporting | Deliver offers from product features that unblock enterprise deals | On Track | Tim Hoolihan | Not specified | 2026-05-12 10:49 | 5/12 - Product and GTM teams aligned, relevant offer go live plans in progress | 5/12 - No Q4 deal is blocked due to delayed offer availability
Supporting | Migrate CCX customers to Webex Contact Center through partner-led motions | Off Track/Delayed | Karthik Sundaram | Melissa Riner | 2026-06-09 15:49 | 758 | City of Boston is first customer to go live with migration tool. The current migration offer is not achieving the intended outcomes. Until the GTM strategy and offer are updated, we anticipate continued challenges in driving improved results.
Supporting | Leverage Cisco’s broader installed base (networking, security, collaboration) to open CX doors. | On Track | Helen Briggs | Not specified | 2026-05-25 11:07 | 5/12 - Continued in progress | 5/12 - This is ongoing throughout the year - John Kiang and team continue to help identify which customers by SL1, SL2, SL3 ahave recently bought large networking, security, collaboration deals that may help sales engage and upsell CX.
Supporting | Task Agent Orchestration Framework | Off Track/Delayed | Manoj Muthavarapu | Manoj Muthavarapu | 2026-05-27 14:02 | No major productization work started on this beyond A2A / transfers | Active productization on this track will begin after we deliver the concierge framework
Supporting | Maintain product quality and availability [WxCCE] | On Track | Krish Padmanabhan | Suresh Hariharan | 2026-06-02 10:30 | May SLA uptime - 99.995% Platform - 100%